## Summary
TraceLMs Cloud — SaaS Implementation Plan: Phase 1 · Phase 2 · Phase 3
Version 0.1.0 · Generated June 24, 2026 · Source: Technical Document v0.1.0
Phase 1 — Persistence & Reliability |  |  | Phase 2 — Authentication & Security |  |  | Phase 3 — Multi-Tenancy & Projects
Timeline | Weeks 1–3 |  | Weeks 3–5 |  | Weeks 5–9
Total Tasks | 4 |  | 7 |  | 5
High Priority | 3 |  | 6 |  | 4
Effort Range | Small–Medium |  | Small–Large |  | Medium–Large
Prerequisite | None |  | Phase 1 |  | Phase 2
Strategic Goal | Stable product |  | Secure product |  | Team product
Combined Portfolio Summary
Total Tasks Across All Phases |  |  | 16
High Priority Tasks |  |  | 13
Estimated Duration |  |  | ~9 weeks (Weeks 1–9)
Key Dependency Chain |  |  | Phase 1 → Phase 2 → Phase 3
Primary Technical Risk |  |  | Auth before network exposure
Primary Business Risk |  |  | Generation state lost on refresh
LEGEND
High Priority | Medium Priority | Low Priority | Small Effort | Medium Effort | Large Effort | To Do

## Phase 1 — Persistence
TraceLMs Cloud — Phase 1: Persistence & Reliability
Version 0.1.0 · Generated June 24, 2026 · Source: Technical Document v0.1.0 · Legend → High Medium Low Small (1–3d) Medium (1–2w) Large (3w+) To Do
Feature | Task | Description | Priority | Effort | Timeline | Dependencies | Risk | User Impact | Status
Generation Persistence
Generation Persistence | Write Generation record on generateAll completion | Add prisma.generation.create() call at the end of the generateAll flow in generate.ts (or routes layer). Fields: requirementText, llmProvider, llmModel, status (IN_PROGRESS → COMPLETED), enhancement, scenarios, testCases, automation (JSON blobs). Also write status=FAILED on any phase error. | High | Small (1–2d) | Week 1 | None — Prisma Generation model already exists in schema | Low — additive DB write; no breaking changes to existing routes | Zero rework after accidental browser close. Sessions feel persistent and trustworthy. | To Do
| GET /api/generation/latest — restore last session on load | New Express route: GET /api/generation/latest. Returns the most recent Generation record (ORDER BY createdAt DESC LIMIT 1). Frontend useTraceLMMessages useEffect calls this on mount and populates all state slices (enhancement, scenarios, testCases, automation) if a record exists. Add a 'Restored from last session' toast notification. | High | Small (1–2d) | Week 1 | Generation write task (above) | Low — read-only route; no mutation risk | Users resume work instantly after browser close or accidental refresh. Transforms the tool from a demo into a usable product. | To Do
| GET /api/generation/history — list past generations | Route returns Generation[] ordered by createdAt DESC, limited to 20 rows. Each record includes: id, requirementText (first 120 chars), llmProvider, llmModel, status, createdAt. Used by the future Generation History UI (Phase 3). Wire now so the data is available without a migration later. | Medium | Small (1d) | Week 1 | Generation write task | Low — read-only | Foundation for project-scoped history in Phase 3. | To Do
Push History Persistence
Push History Persistence | Add PushRecord Prisma model | New model PushRecord: id (cuid), fingerprint (String @unique), xrayKey (String), xrayUrl (String), pushedAt (DateTime), generationId (String?, FK to Generation). Run prisma migrate dev. Seed nothing — table starts empty. | High | Small (2–4h) | Week 2 | None — new model, no dependencies | Low — additive migration only; no existing data affected | Prerequisite for persistent deduplication. | To Do
| Migrate PushHistoryStore from in-memory to DB | Replace the in-memory Map in PushHistoryStore.ts with Prisma calls: put() → prisma.pushRecord.upsert(where: {fingerprint}, ...). has() → prisma.pushRecord.findUnique(). getAll() → prisma.pushRecord.findMany(). clear() → prisma.pushRecord.deleteMany(). Keep the public interface identical so no callers need to change. | High | Small (1d) | Week 2 | PushRecord model migration | Medium — DB write on every push; ensure upsert is atomic to prevent race conditions on concurrent pushes | Duplicate detection survives server restarts and deployments. Resolves Technical Debt TD-6. | To Do
UX Cleanup — Dead Tabs
UX Cleanup — Dead Tabs | Add 'Coming Soon' banner to Projects and LLM Providers tabs | Replace the empty tab bodies in ProjectsTab.tsx and LLMProvidersTab.tsx with a centered banner: icon + heading 'This feature is coming soon' + optional timeline hint. Use existing --surface-2, --text-secondary tokens. Do NOT remove the tabs from the sidebar — their slot is reserved for Phase 3 (Projects) and Phase 4 (LLM Providers). | High | Small (2–4h) | Week 1 | None | Low — cosmetic only | Eliminates user confusion from dead-end navigation. Improves trust. Resolves UX gap identified in Section 11 and Recommendation R7. | To Do
| Add empty-state illustrations to blank generation tabs | Enhancement, Scenarios, TestCases, Automation tabs show blank content before generation. Add an empty-state component: icon + heading + sub-text ('Run generation to see results here'). Use the existing Tip.tsx component pattern. Consistent with the design system — no new tokens required. | Medium | Small (2–4h) | Week 2 | None | Low — cosmetic only | First-time users understand the workflow without a tooltip or guide. Reduces support questions about why tabs appear empty. | To Do
Phase 1 Complete: 6 tasks · 3 features · ~3 weeks · Transforms TraceLMs Cloud from a demo into a persistent, trustworthy product.

## Phase 2 — Auth & Security
TraceLMs Cloud — Phase 2: Authentication & Single-User Security
Version 0.1.0 · Generated June 24, 2026 · Source: Technical Document v0.1.0 · Prerequisite: Phase 1 complete · Legend → High Medium Low Small Medium Large To Do
Feature | Task | Description | Priority | Effort | Timeline | Dependencies | Risk | User Impact | Status
User Model & Auth Core
User Model & Auth Core | Add User Prisma model | New model User: id (cuid), email (String @unique), passwordHash (String), createdAt (DateTime @default(now)), lastLoginAt (DateTime?), isActive (Boolean @default(true)). Run prisma migrate dev. No seed user — first user registers via POST /api/auth/register. Foreign-key User.id on Project.ownerId and Generation.userId (nullable for legacy records). | High | Small (2–4h) | Week 3 | Phase 1 complete (Generation model must exist before adding FK) | Low — additive migration; existing Generation rows get userId = null | Foundation for all subsequent SaaS features. Without a User model, multi-tenancy (Phase 3) and billing cannot be built. | To Do
| POST /api/auth/register — create first user | Route: POST /api/auth/register. Body: { email, password }. Validates email format + password min length (12 chars). Hashes password with bcrypt (cost factor 12). Creates User record. Returns 201 with { userId, email } (no token yet — must login). IMPORTANT: Disable this route after first user is created (env flag: ALLOW_REGISTRATION=true). This prevents open registration in single-user mode. | High | Small (1d) | Week 3 | User model migration | Medium — must disable after first registration; document this clearly in .env.example | Enables the team to bootstrap the first user account securely. | To Do
| POST /api/auth/login — issue JWT | Route: POST /api/auth/login. Body: { email, password }. Finds User by email. Compares password with bcrypt.compare(). On success: issues JWT (jsonwebtoken). Payload: { userId, email, iat, exp }. Expiry: 8 hours (ACCESS_TOKEN_EXPIRY env var). Returns: { token, expiresAt }. On failure: 401 with generic message (never reveal whether email exists — prevents enumeration). | High | Small (1d) | Week 3 | User model + bcrypt + jsonwebtoken packages installed | High — JWT secret (JWT_SECRET env var) must be 32+ chars and stored securely; document rotation procedure in .env.example | Users can authenticate with email and password. All subsequent API calls use Bearer token. | To Do
Auth Middleware
Auth Middleware | JWT auth middleware for all /api routes | Express middleware: src/middleware/auth.ts. Reads Authorization: Bearer <token> header. Verifies JWT with JWT_SECRET. On valid: attaches req.user = { userId, email }. On invalid/missing: returns 401 { error: 'Unauthorised' }. Mount BEFORE all route groups in server.ts EXCEPT: /api/health, /api/auth/login, /api/auth/register (public routes). All generation, settings, Jira, Xray, and parse routes become protected. | High | Small (1d) | Week 3 | Login route (JWT issuance must exist before middleware can validate) | High — misconfiguration leaves all routes unprotected; write integration test that verifies 401 is returned on all /api/generate/* without token | Any request to any route without a valid token is rejected. LLM API keys in the DB are no longer accessible to unauthenticated callers. | To Do
| Login page component (React) | New route /login in the React SPA. Simple form: email + password fields + Login button. On submit: POST /api/auth/login → store token in localStorage ('tracelms-token'). On success: redirect to /. On failure: show inline error. App.tsx: on mount, check for token in localStorage; if missing/expired → redirect to /login. Add logout button in sidebar footer: clears token + redirects to /login. | High | Medium (2–3d) | Week 3–4 | JWT auth middleware (token must be validated before granting access to the SPA) | Medium — token expiry handling: if a 401 is received mid-session, redirect to login with a 'Session expired' message rather than silently failing | Users log in with email and password. The app is no longer accessible to anyone who can reach port 3000. | To Do
Rate Limiting
Rate Limiting | express-rate-limit on generation endpoints | Install express-rate-limit. Apply to all /api/generate/* routes: windowMs: 60_000 (1 min), max: 10 requests per IP. Apply a stricter limit on /api/auth/login: 5 attempts per 15 minutes per IP (brute force protection). On limit: return 429 with Retry-After header. Frontend: detect 429 and show 'Rate limit reached — try again in X seconds.' | High | Small (2–4h) | Week 4 | Auth middleware (rate limiter should be applied after auth is in place) | Low — express-rate-limit is a drop-in middleware; misconfigured limits could block legitimate heavy users — set limits conservatively and monitor | Protects LLM API quotas from abuse. Prevents runaway costs from programmatic or accidental repeated calls. | To Do
Input Validation
Input Validation | Requirement text length validation and sanitization | In generate.ts routes: validate requirements text length (max 50,000 chars — configurable via MAX_REQUIREMENT_CHARS env var). Return 400 if exceeded. Basic sanitization: trim whitespace, reject null bytes. Do NOT sanitize for HTML/XSS (text goes to LLM, not rendered as HTML in backend). Add frontend character counter in RequirementsTab.tsx with warning at 80% of limit. | High | Small (1d) | Week 4 | None | Low — validation is additive; existing valid inputs are unaffected | Prevents oversized payloads from timing out or exhausting LLM token limits. Gives users clear feedback before hitting a server-side limit. | To Do
HTTPS & Hardening
HTTPS & Hardening | HTTPS enforcement via reverse proxy (Nginx/Caddy) | Configuration guide + template files (not application code changes). Caddy (recommended): Caddyfile with automatic TLS via Let's Encrypt. Nginx alternative: nginx.conf template with proxy_pass to localhost:3000, ssl_certificate paths, HSTS header (max-age=31536000; includeSubDomains). Update CORS in server.ts to allow the production domain (ALLOWED_ORIGINS env var). Document in README: 'TLS is required before sharing any URL externally.' | High | Small (2–4h) | Week 4 | Domain name + server with public IP (infrastructure prerequisite) | Medium — certificate renewal must be automated (Caddy handles this automatically; Nginx requires a cron job with certbot renew) | All traffic — including API keys in request bodies — is encrypted in transit. Resolves the highest-severity security gap in Section 10. | To Do
Phase 2 Complete: 8 tasks · 4 features · ~3 weeks · TraceLMs Cloud is now protected by auth, rate limiting, input validation, and HTTPS.

## Phase 3 — Multi-Tenancy
TraceLMs Cloud — Phase 3: Multi-Tenancy & Project Management
Version 0.1.0 · Generated June 24, 2026 · Source: Technical Document v0.1.0 · Prerequisite: Phase 1 + Phase 2 complete · Legend → High Medium Low Small Medium Large To Do
Feature | Task | Description | Priority | Effort | Timeline | Dependencies | Risk | User Impact | Status
User & Project Schema
User & Project Schema | Scope Settings per user (replace global 'id=global' row) | Current Settings table has a single row with id='global'. Add userId (String, FK to User) to Settings. Run migration. Seed: for the existing global row, set userId = the first User.id. SettingsService: all read/write operations filter by req.user.userId. On first login, if no Settings row exists for this user, create one with defaults. | High | Medium (2–3d) | Week 5 | Phase 2 complete (User model + auth middleware must exist) | Medium — existing single-row Settings data must be migrated to the first user; do not DROP the existing row — UPDATE it with userId | Multiple users can have independent LLM, Jira, and Xray configurations. No more shared settings row that concurrent users overwrite. | To Do
| Scope Generation history per user | Add userId (String, FK to User, NOT NULL) to Generation model. Migration: set userId = first User.id for all existing rows. All generation routes: pass req.user.userId when creating Generation records. GET /api/generation/latest and GET /api/generation/history filter by userId. No user can see another user's generation history. | High | Small (1d) | Week 5 | User model (Phase 2) + Generation persistence (Phase 1) | Low — additive FK; existing rows migrated to first user | Each user has their own isolated generation history. Foundation for project-scoped history in the next task. | To Do
Project Management
Project Management | Project CRUD routes (/api/projects) | Activate the existing Prisma Project model. Implement routes: POST /api/projects (create), GET /api/projects (list for req.user), GET /api/projects/:id (detail), PATCH /api/projects/:id (update name/status), DELETE /api/projects/:id (soft-delete: set status=ARCHIVED). All routes filter by ownerId = req.user.userId. Project fields: name, key (Jira project key), status (DRAFT/ACTIVE/ARCHIVED), ownerId. Link Generation.projectId on creation if a project is active. | High | Medium (2–3d) | Week 6 | User schema scoping (Settings + Generation per user) | Low — the Project Prisma model already exists; routes are additive | Teams can organise generations by project. Multiple Jira projects can have separate test generation histories. | To Do
| Projects tab UI — CRUD interface | Replace the 'Coming Soon' banner in ProjectsTab.tsx with a full UI: Project list (cards with name, key, status badge, generation count, last activity). Create Project modal (name, key fields). Edit/Archive actions per project. Active project selector: selecting a project sets it as the active context — new generations are automatically linked to it. Display active project name in the sidebar footer (below the logout button). Use existing design tokens: --surface-2, --accent, --radius-md. | High | Large (3–4d) | Week 6–7 | Project CRUD routes | Medium — active project state must be preserved across page loads (store in localStorage as activeProjectId) | QA teams can manage multiple Jira projects in one TraceLMs Cloud instance. Activates the Projects tab for the first time. | To Do
| Generation history view per project | Inside the Projects tab (project detail view): a table of past generations for the selected project. Columns: date, requirement preview (first 80 chars), LLM provider, model, status, test case count, actions (Load, Delete). 'Load' action: calls GET /api/generation/:id and restores full state (enhancement, scenarios, testCases, automation) into the active generation context. Replaces the current 'restore from latest' behaviour with an explicit history picker. | High | Medium (2–3d) | Week 7 | Project CRUD + Generation scoping per user | Medium — restoring a past generation must confirm if there is unsaved current work (show a 'You have unsaved work — discard and load?' confirmation guard) | Users can compare past generation runs, restore previous results, and build an institutional library of test generation sessions. | To Do
Stakeholder Management
Stakeholder Management | Stakeholder invite and role assignment UI | Activate the Prisma Stakeholder model. In the project detail view: 'Team' section listing current stakeholders (email, role, added date). Add Stakeholder form: email + role (QA Lead, Product Owner, Developer, Observer). POST /api/projects/:id/stakeholders (add), DELETE /api/projects/:id/stakeholders/:sid (remove). NOTE: Email notification for invite is a Phase 5 deliverable — at this stage, invite is recorded in DB only; the invitee must be told manually. | Medium | Medium (2–3d) | Week 8 | Project CRUD routes + Stakeholder Prisma model (already exists in schema) | Low — no email sending yet; Stakeholder records are informational at this stage | Project members are formally recorded. Foundation for the Phase 5 stakeholder approval and notification workflow. | To Do
| Per-user settings scoping — Jira project key in context | When a user selects an active Project in the Projects tab, auto-populate the Jira Project Key field in SettingsTab.tsx with the project's key. This eliminates copy-paste errors when switching between Jira projects. Store the mapping: Project.key → Settings.jiraProjectKey. On project switch, offer: 'Update Jira project key to [KEY]? Yes / Keep current.' | Medium | Small (1d) | Week 8 | Project CRUD + per-user Settings | Low — settings update is user-confirmed; no automatic overwrite | Switching between Jira projects is frictionless. Reduces misconfiguration risk when generating tests for multiple projects. | To Do
Phase 3 Complete: 7 tasks · 3 features · ~5 weeks · TraceLMs Cloud becomes a multi-user team product with project organisation and stakeholder tracking.

## Risk Register
TraceLMs Cloud — Risk Register (Phase 1–3)
ID | Phase | Risk | Severity | Likelihood | Impact | Mitigation | Owner
R-01 | Phase 1 | Generation state lost on browser refresh (current state) | High | High | Users lose all generated artifacts on every refresh — single biggest UX gap | Phase 1 Task 1 (write Generation record) + Task 2 (restore on load) directly resolves this. | Engineering
R-02 | Phase 1 | PushHistoryStore resets on server restart | Medium | High | Duplicate test cases re-pushed to Xray after any deployment or restart | Phase 1 Task 4–5: migrate PushHistoryStore to DB-backed PushRecord model. | Engineering
R-03 | Phase 2 | No authentication — open attack surface | Critical | High | Any user who can reach port 3000 has full control of all settings, LLM API keys, and generation routes | Phase 2 fully resolves: JWT auth + middleware + login page. Do not expose any public URL before Phase 2 is complete. | Engineering + Ops
R-04 | Phase 2 | JWT_SECRET compromise or rotation failure | Critical | Low | If JWT_SECRET is lost or exposed, all active sessions are immediately invalidated and the secret must be rotated | Store JWT_SECRET in a secrets manager (not .env file in production). Document rotation procedure: rotate secret → all users must re-login. | Engineering + Security
R-05 | Phase 2 | ENCRYPTION_KEY loss makes all stored keys unreadable | Critical | Low | If ENCRYPTION_KEY changes, all encrypted API keys in the Settings table become permanently unreadable | Backup ENCRYPTION_KEY in a separate secrets store. Never rotate without first decrypting and re-encrypting all stored secrets. | Ops
R-06 | Phase 2 | Brute-force login attacks | High | Medium | Without rate limiting on /api/auth/login, an attacker can enumerate email addresses and brute-force passwords | Phase 2 Task 6: express-rate-limit on login (5 attempts per 15 min per IP). Phase 2 Task 8: HTTPS (prevents credential interception). | Engineering
R-07 | Phase 2 | LLM API cost overrun (no rate limiting) | Medium | High | No rate limiter on generation endpoints — unrestricted calls can exhaust LLM API quotas rapidly | Phase 2 Task 6: express-rate-limit on /api/generate/* (10 req/min/IP). | Engineering
R-08 | Phase 3 | Settings migration from global row to per-user fails | High | Low | If the existing global Settings row is accidentally dropped during migration, all stored API keys are lost | UPDATE existing row (set userId = first User.id) — do NOT DELETE/INSERT. Take a DB snapshot before running the migration. | Engineering
R-09 | Phase 3 | Supabase connection limit under concurrent users | Medium | Medium | Session pooler has a connection limit; under multi-user load, Prisma may exhaust available connections | Monitor connection count in Supabase dashboard. Set Prisma connection_limit in DATABASE_URL. Upgrade Supabase plan if limit is approached. | Ops
R-10 | Phase 3 | Active project context lost on session expiry | Low | Medium | If a user's JWT expires mid-session, the active project selection (stored in localStorage) may desync from the server state | On session restore (login page redirect), reload the active project from localStorage and validate it exists via GET /api/projects/:id before restoring context. | Engineering

## Technical Debt
TraceLMs Cloud — Technical Debt Register (from v0.1.0 Technical Document)
ID | Description | Location | Severity | Effort | Resolved by Phase | Notes
TD-1 | App.tsx is ~45KB single file holding all UI state, ref layer, navigation, and tab routing | frontend/src/App.tsx | Medium | Large | Phase 3+ | Split into context providers + smaller root component. Not blocking for Phases 1–3 but will become pain point in Phase 3 with project state.
TD-2 | generate.ts is ~470 lines; automation batching logic should be extracted to a service class | src/routes/generate.ts | Low | Medium | Phase 4 | Extract runAutomationBatched and mergeAutomationResults to src/services/llm/AutomationBatchService.ts.
TD-3 | Three slightly different Settings type shapes (BE types, SettingsService, FE types.ts) | src/types/index.ts, src/services/SettingsService.ts, frontend/src/types.ts | Low | Small | Phase 2 | Consolidate into a single shared type. Use a shared package or copy from BE → FE via a types sync script.
TD-4 | LLMProvider DB table exists but all routes use static llmModelsByProvider constant | frontend/src/types.ts, src/routes/generate.ts | Medium | Medium | Phase 4 | Phase 4 adds Prompt Management UI — at that point, activate GET /api/llm-providers and replace the static constant.
TD-5 | No integration tests for Express routes — unit tests only | src/**/__tests__/ | Medium | Large | Phase 2 | Add supertest integration tests covering: 401 on all /api routes without token, 429 on rate-limit breach, and full generate→push flow.
TD-6 | PushHistoryStore is in-memory — resets on server restart | src/services/storage/PushHistoryStore.ts | High | Small | Phase 1 | RESOLVED by Phase 1 Task 4–5: migrate to Prisma PushRecord model.
TD-7 | No streaming cancellation (AbortController) — server continues after user navigates away | frontend/src/api/client.ts, src/routes/generate.ts | Medium | Medium | Phase 3 | Add AbortController in streamPost(). Pass signal to fetch(). On route: detect closed connection and abort LLM call.
TD-8 | docx and pptxgenjs in package.json — usage unconfirmed in v0.1.0 | package.json (backend) | Low | Small | Immediate | Audit package.json. Remove unused packages to reduce bundle size and attack surface.
TD-9 | Settings sent in every API request body (API keys transmitted repeatedly) | frontend/src/hooks/useTraceLMMessages.ts | Medium | Medium | Phase 2 | Post-Phase 2: move to server-side session token (R8 in recommendations). API keys stored in DB, retrieved server-side only.
TD-10 | PushHistoryStore.clear() has no confirmation guard in the UI | frontend/src/tabs/TestCasesTab.tsx | Low | Small | Phase 1 | Add inline confirm guard to 'Clear Xray History' button (same pattern as Clear All button in RequirementsTab).