## Why Phase 3.5 Exists
Phase 3.5 — RBAC Foundation: Why This Bridging Phase Exists
Version 0.1.0 base · Inserted between Phase 3 (Multi-Tenancy) and Phase 4 (AI Quality) · Generated June 24, 2026
Phase | RBAC State After Completion | Problem
Phase 2 — Auth | JWT auth gates all routes. Single User model with email + password. No roles whatsoever. | Every authenticated user has identical access to every route. A Viewer can push to Xray, change global settings, and delete projects.
Phase 3 — Multi-Tenancy | Stakeholder model adds a role field (QA Lead, Product Owner, Developer, Observer). Role is a text label — stored in DB, displayed in UI, but never read by any middleware or route guard. | Multi-tenant system with zero permission enforcement. All users share identical server-side capabilities regardless of label. Inviting a Viewer grants them full Owner-equivalent access.
Phase 3.5 — RBAC Foundation ← THIS PHASE | OrgRole enum (Owner / Admin / Editor / Viewer) enforced on User model. ProjectRole enum (Lead / Editor / Reviewer / Viewer) enforced on ProjectMember. Permission middleware guards all sensitive routes. UI hides/disables actions the current user cannot perform. | RESOLVED. Users operate within enforced permission boundaries. Viewer cannot push, Admin cannot change global settings, Owner bootstrap prevents lockout.
Phase 4–5 — AI Quality & Differentiators | RBAC from Phase 3.5 is in place. New features (prompt editing, traceability, bulk ops) inherit permission checks automatically. | No gap — Phase 3.5 ensures new features are gated correctly at launch.
Phase 6 — Enterprise Readiness | Extends Phase 3.5 RBAC with: fine-grained permission matrix UI, SCIM provisioning, SSO/SAML role mapping, org-level audit dashboard. | Phase 6 RBAC is additive — it refines and extends Phase 3.5, not a rewrite. Phase 3.5 is the prerequisite.
Design Authority Note
Q: Why not just wait for Phase 6?
Phase 6 Enterprise RBAC requires SSO, SAML, SCIM, and an org model — large-effort features targeting enterprise buyers. Building on an unprotected foundation for 3 more phases (4, 5, 6) means every new feature ships with zero permission enforcement. A Viewer in Phase 4 can edit prompts. A Viewer in Phase 5 can bulk-push to Xray. Phase 3.5 closes this window with one focused sprint.
Q: Why not fold RBAC into Phase 3?
Phase 3 is already large (7 tasks, 5 weeks). Adding RBAC enforcement increases scope and risk. Separating it into Phase 3.5 keeps Phase 3 focused on data architecture (per-user settings, generation scoping, project CRUD) and gives RBAC a clean, dedicated implementation window.
Q: What Phase 3.5 does NOT include
Fine-grained permission matrix UI (Phase 6). SAML/OIDC role mapping (Phase 6). SCIM user provisioning (Phase 6). Audit log (Phase 6 — AuditLog model). These are enterprise features. Phase 3.5 delivers the enforcement foundation; Phase 6 delivers the enterprise management layer on top.

## Role Model Reference
Phase 3.5 — Role Model: OrgRole × ProjectRole Matrix
OrgRole — Assigned to the User model (organisation-level scope)
OrgRole | Assigned To | Global Settings | User Management | Create Project | View All Projects | Billing (Phase 6)
Owner | First registered user; manually assigned | ✓ Full | ✓ Full | ✓ | ✓ | ✓
Admin | Invited by Owner; manages projects and users | ✗ Read | ✓ Invite | ✓ | ✓ | ✗
Editor | Standard team member; creates and pushes | ✗ | ✗ | ✓ | Own | ✗
Viewer | Read-only observer; can review but not change | ✗ | ✗ | ✗ | Own | ✗
ProjectRole — Assigned to ProjectMember (project-level scope, overrides lower OrgRole)
ProjectRole | Typical User | Generate | Edit Test Cases | Push to Xray | Manage Project | Invite Members
Lead | QA Lead, project owner | ✓ | ✓ | ✓ | ✓ | ✓
Editor | QA Engineer, test author | ✓ | ✓ | ✓ | ✗ | ✗
Reviewer | Product Owner, BA reviewing tests | ✓ | ✗ | ✗ | ✗ | ✗
Viewer | Stakeholder, read-only observer | ✗ | ✗ | ✗ | ✗ | ✗
Precedence Rules (enforced in src/middleware/permissions.ts)
Rule 1 — OrgRole Owner overrides all
A User with OrgRole=Owner has full access to every route and every project, regardless of ProjectRole. This prevents lockout.
Rule 2 — ProjectRole is additive, not restrictive upward
An Editor (OrgRole) assigned Lead (ProjectRole) on a project inherits all Lead capabilities within that project, but cannot access routes requiring Admin+ OrgRole.
Rule 3 — Viewer is always read-only
OrgRole=Viewer or ProjectRole=Viewer can never trigger a mutation route (POST/PATCH/DELETE on any resource, and POST /api/xray/push). The 403 response must include: { error: 'Insufficient permissions', required: 'Editor+', current: 'Viewer' }.
Rule 4 — Phase 6 inherits, not replaces
Phase 6 Enterprise RBAC (SAML role mapping, fine-grained matrix UI) maps IdP roles to these four OrgRole values. No schema migration is needed — Phase 6 adds configuration on top of the Phase 3.5 enum.

## Phase 3.5 — RBAC Plan
TraceLMs Cloud — Phase 3.5: RBAC Foundation (Bridging Phase)
Version 0.1.0 base · Generated June 24, 2026 · Prerequisite: Phase 3 complete · Estimated duration: ~2 weeks (Weeks 9–11) · Unlocks: Phase 4, 5, and 6 have enforced permissions at launch
Feature | Task | Description | Priority | Effort | Timeline | Dependencies | Risk | User Impact | Status
Role Model Extension
Role Model Extension | Add OrgRole enum + role field to User model | New Prisma enum OrgRole { OWNER ADMIN EDITOR VIEWER }. Add role OrgRole @default(VIEWER) to User model. Migration: UPDATE User SET role = 'OWNER' WHERE id = (SELECT id FROM User ORDER BY createdAt ASC LIMIT 1). All other existing users default to EDITOR (not VIEWER — avoid locking out existing team). Add OWNER env guard: if only 1 user exists at registration, auto-assign OWNER. Resolves: Phase 3's Stakeholder role labels had no DB-level enforcement. | High | Small (1d) | Week 9 | Phase 3 complete (User model + Project model must exist) | Medium — UPDATE migration must not set all users to VIEWER; carefully scope to EDITOR default to avoid accidental lockout | Permission enforcement becomes possible. Without this enum, no middleware can distinguish an Owner from a Viewer. | To Do
| Add ProjectRole enum + ProjectMember model | New Prisma enum ProjectRole { LEAD EDITOR REVIEWER VIEWER }. Replace the Stakeholder model's free-text role field with projectRole ProjectRole. Rename Phase 3 Stakeholder → ProjectMember for clarity (update all references in routes + UI). Add projectId + userId + projectRole as a composite unique key. Migration: map existing Stakeholder.role text → nearest ProjectRole enum value (QA Lead → LEAD, Product Owner → REVIEWER, Developer → EDITOR, Observer → VIEWER). | High | Small (1d) | Week 9 | OrgRole migration (above) + Phase 3 Stakeholder model | Low — enum mapping of existing text roles is deterministic; no existing ProjectMember data is deleted | Project-level roles are now enforced. A Reviewer cannot push to Xray even if their OrgRole would normally allow it within the project. | To Do
| Expose role in JWT payload + /api/auth/me route | Update POST /api/auth/login: include role: OrgRole in JWT payload. Add GET /api/auth/me route: returns { userId, email, role, createdAt } from DB (not just from token — allows role changes to take effect without re-login). Frontend: call GET /api/auth/me on mount and store role in React context (new AuthContext.tsx). Role is available to all components for conditional rendering. | High | Small (1d) | Week 9 | OrgRole on User model + auth middleware (Phase 2) | Low — GET /api/auth/me is protected by existing auth middleware; no additional security surface introduced | Components can read the current user's role without re-decoding the JWT. Role changes by an Owner take effect on the next /api/auth/me poll. | To Do
Permission Middleware
Permission Middleware | Build src/middleware/permissions.ts — can() helper | Create a typed permission helper: can(user: AuthUser, action: Action, resource?: Resource): boolean. Actions: 'settings:write', 'user:manage', 'project:create', 'project:delete', 'generate:run', 'xray:push', 'testcase:edit', 'prompt:edit'. Resource (optional): { projectId, projectRole? } — looked up from DB when project-scoped. Implement the precedence rules from the Role Model sheet: OWNER bypasses all checks; VIEWER blocked from all mutations. Export requireRole(roles: OrgRole[]) and requireProjectRole(roles: ProjectRole[]) Express middleware factories built on top of can(). | High | Medium (2d) | Week 10 | OrgRole + ProjectRole on DB (tasks above) | High — this is the single most critical file in Phase 3.5; a logic error here grants or denies access incorrectly. Write unit tests covering all role × action combinations before deploying. | All sensitive actions are gated by role. A Viewer calling POST /api/xray/push receives 403 with a clear error message. | To Do
| Apply requireRole guards to all sensitive routes | Mount permission middleware on routes in server.ts (after auth middleware): PATCH/DELETE /api/settings → requireRole([OWNER]) — only Owner changes global settings. GET/POST /api/users → requireRole([OWNER, ADMIN]) — user management. POST /api/projects → requireRole([OWNER, ADMIN, EDITOR]) — Viewers cannot create projects. DELETE /api/projects/:id → requireRole([OWNER, ADMIN]). POST /api/xray/push → requireProjectRole([LEAD, EDITOR]) — Reviewers + Viewers cannot push. POST /api/generate/* → requireProjectRole([LEAD, EDITOR, REVIEWER]) — Viewers cannot generate. POST /api/prompts/* (Phase 4, added later) → requireRole([OWNER, ADMIN]). | High | Medium (2d) | Week 10 | permissions.ts + unit tests passing | High — must test every protected route with a Viewer token and confirm 403; use a Postman/supertest matrix: role × route × expected status code | Server enforces permissions independently of the UI. Even a user who bypasses the frontend cannot perform unauthorised actions. | To Do
| Add project-scoped role check to Xray + Generate routes | For routes that operate within a project context (POST /api/xray/push, all /api/generate/* routes): extract projectId from request body. Look up ProjectMember record for { projectId, userId }. If found: use ProjectRole for permission check (overrides OrgRole downward). If not found: fall back to OrgRole. This allows a Viewer (OrgRole) who is a Lead on a specific project to generate and push within that project. | High | Small (1d) | Week 10 | requireRole + requireProjectRole middleware | Medium — DB lookup on every generate/push call adds latency; cache ProjectMember role in request object (set in middleware, read in route handler) | Permissions are correctly scoped per-project. A QA Lead on Project A cannot push results from Project B. | To Do
UI Permission Awareness
UI Permission Awareness | AuthContext — role available to all React components | Create frontend/src/contexts/AuthContext.tsx. Context value: { user: { userId, email, role } ¦ null, logout(): void, projectRole(projectId): ProjectRole ¦ null }. Provider wraps App.tsx. On mount: call GET /api/auth/me → populate context. On 401: clear token + redirect to /login. Export useAuth() hook. All permission-conditional rendering uses useAuth() — no prop-drilling role values through component trees. | High | Medium (2d) | Week 10 | GET /api/auth/me route + React context pattern | Low — React context for auth is a standard pattern; the only risk is stale role data if an Owner changes another user's role mid-session; mitigate with a 60-second polling interval on /api/auth/me | Components read role from context, not props. Adding a new permission check anywhere in the app requires one line: const { user } = useAuth(). | To Do
| Disable/hide destructive actions for Viewer role | In all tabs, wrap mutation actions with role checks from useAuth(): Push to Xray button → disabled + tooltip 'Requires Editor or above' if Viewer. Clear Xray History button → hidden for Viewer. Delete Project button in ProjectsTab → hidden for Viewer and Reviewer. Save Settings button in SettingsTab → disabled for non-Owner with tooltip. Disabled state: existing design token pattern (opacity + cursor: not-allowed). Do NOT remove buttons — show them as disabled so Viewers understand what capabilities exist (progressive disclosure). | High | Medium (2d) | Week 11 | AuthContext (useAuth hook must be available before UI gating) | Low — UI gating is a defence-in-depth layer; the server-side route guards (above) are the authoritative enforcement; UI state is cosmetic but reduces user confusion | Viewers see a clear, consistent UI that reflects their capabilities. No misleading buttons that return a confusing 403 when clicked. | To Do
| Role badge in sidebar footer | In the sidebar footer (below the user email and logout button): add a small role badge pill using existing --radius-full token. Colors: OWNER → --accent (teal), ADMIN → navy, EDITOR → green, VIEWER → gray. Text: role name in --text-xs, --weight-semibold. Tooltip on hover: full role description (e.g. 'Editor — can generate and push to Xray'). On project context active: show both OrgRole and effective ProjectRole ('Editor · Lead on Project Alpha'). This gives users immediate visual confirmation of their access level. | Medium | Small (1d) | Week 11 | AuthContext + role data from /api/auth/me | Low — cosmetic; no functional impact | Users always know their permission level without navigating to settings. Reduces 'why can't I push?' support questions. | To Do
Owner Bootstrap & User Mgmt
Owner Bootstrap & User Mgmt | Owner bootstrap — auto-assign OWNER to first registered user | In POST /api/auth/register: after creating the User record, check if User count === 1 (the newly created user is the only one). If true: UPDATE User SET role = 'OWNER' WHERE id = newUser.id. Log: 'First user registered — assigned OrgRole: OWNER'. Add a check in GET /api/auth/me: if no OWNER exists in the User table (edge case: OWNER deleted themselves), set the oldest Admin as OWNER. | High | Small (2–4h) | Week 9 | OrgRole on User model | Low — count check is atomic; the only risk is a race condition if two users register simultaneously (mitigate with a DB-level unique index on role=OWNER — only one allowed) | The first user automatically becomes the system Owner. No manual DB intervention required to bootstrap a new instance. | To Do
| GET + PATCH /api/users — Owner-only user management routes | GET /api/users → requireRole([OWNER, ADMIN]): returns all User records { id, email, role, createdAt, lastLoginAt, isActive }. PATCH /api/users/:id/role → requireRole([OWNER]): body { role: OrgRole }. Validates: cannot demote the last OWNER. Cannot promote to OWNER if one already exists (single-Owner in Phase 3.5; multi-Owner supported in Phase 6). PATCH /api/users/:id/status → requireRole([OWNER, ADMIN]): body { isActive: boolean } — deactivate users without deleting their data. | High | Small (1d) | Week 9 | OrgRole migration + auth middleware | Medium — OWNER demotion guard is critical; if the last OWNER is demoted, the instance becomes unmanageable; enforce at DB level: before UPDATE, count remaining OWNERs | Owner can manage all users and roles. Admin can deactivate users but cannot change roles. | To Do
| User Management UI in SettingsTab — Owner/Admin only | Add a new 'Team' section in SettingsTab.tsx (visible only to OrgRole OWNER or ADMIN). Table: columns Email, Role (dropdown — OWNER can change any; ADMIN sees read-only for OWNER rows), Status (Active/Deactivated toggle), Last Login. Owner can: change any user's role (except demoting last OWNER), deactivate/reactivate. Admin can: deactivate/reactivate users below Admin level; cannot change roles. Viewer and Editor: Team section is hidden entirely (not disabled — hidden). Uses existing table styling tokens from the design system. | High | Medium (2d) | Week 11 | GET + PATCH /api/users routes + AuthContext | Low — UI is additive; existing SettingsTab layout has room for a new section | Owner and Admin can manage team access entirely from the UI. No DB or server access required for day-to-day user management. | To Do
Phase 3.5 Complete: 12 tasks · 4 features · ~2 weeks (Weeks 9–11) · Every subsequent feature (Phase 4–6) launches with enforced permissions. Phase 6 Enterprise RBAC is additive on top of this foundation — no schema migration needed.

## Impact on Phase 4–6
Phase 3.5 — Impact on Future Phases: What Each Phase Inherits
Phase | Feature | How Phase 3.5 RBAC Applies | Gate Required
Phase 4 AI Quality | Prompt Management UI (view + edit system prompts) | requireRole([OWNER, ADMIN]) on POST/PUT /api/prompts/*. Only Owner and Admin can edit prompts that affect all users. Editor and Viewer see prompts as read-only. | OWNER / ADMIN only
Phase 4 AI Quality | Inline Test Case Editing | requireProjectRole([LEAD, EDITOR]) on PATCH /api/testcases/:id. Reviewers and Viewers can read test cases but cannot modify them before Xray push. | LEAD / EDITOR
Phase 4 AI Quality | Generation Feedback Loop (thumbs up/down per test case) | requireProjectRole([LEAD, EDITOR, REVIEWER]) — Reviewers can give feedback as part of their role; Viewers cannot. | LEAD / EDITOR / REVIEWER
Phase 5 Differentiators | Bi-directional Traceability (trace-map route + matrix view) | requireProjectRole([LEAD, EDITOR, REVIEWER]) to view traceability matrix. requireProjectRole([LEAD, EDITOR]) to trigger trace-map generation. Viewers see the matrix read-only. | LEAD / EDITOR (generate) LEAD / EDITOR / REVIEWER (view)
Phase 5 Differentiators | Bulk Operations (bulk Xray push, bulk export) | requireProjectRole([LEAD, EDITOR]) on POST /api/xray/push with multiple IDs. Bulk export (CSV/Excel) is read-only — available to all roles including Viewer. | LEAD / EDITOR (push) All roles (export)
Phase 5 Differentiators | Analytics Dashboard | requireRole([OWNER, ADMIN, EDITOR]) for full analytics. Viewer gets a summary-only view (no per-user breakdowns). Protects sensitive data like LLM cost-per-user. | EDITOR+ (full) VIEWER (summary only)
Phase 6 Enterprise | Fine-grained permission matrix UI (Phase 6 RBAC feature) | Phase 6 adds a UI to configure which actions each role can perform, stored in a new PermissionOverride table. The can() helper in permissions.ts checks PermissionOverride first, then falls back to Phase 3.5 defaults. No schema migration needed — Phase 3.5 enums are preserved. | OWNER only (admin panel)
Phase 6 Enterprise | SAML / OIDC role mapping | IdP group claims (e.g. Okta group 'QA-Leads') map to OrgRole enum values. Mapping stored in a new SSOConfig model. Phase 3.5 OrgRole enum is the target of all SAML role mappings — no new role concept introduced in Phase 6. | OWNER only (SSO configuration)
Phase 6 Enterprise | SCIM 2.0 user provisioning | SCIM /Users endpoint creates User records with the provisioned role (mapped from IdP attributes → OrgRole enum). Phase 3.5 Owner bootstrap guard applies: SCIM cannot provision a second OWNER without explicit Owner approval. | Provisioned by IdP Approved by OWNER
Phase 6 Enterprise | Audit Log (AuditLog Prisma model) | Phase 6 adds audit logging. The AuditLog.userId FK references the User model from Phase 3.5. The AuditLog.action field will include all Phase 3.5-gated actions (SETTINGS_CHANGE, ROLE_CHANGE, XRAY_PUSH, etc.). | OWNER / ADMIN (view audit log)