## Overview
TraceLMs Cloud — Phase 5.5: Document Generation Hub
Implementation Plan v0.1 · Date: June 26, 2026 · Status: DRAFT — Pending TDD Sign-Off
PHASE SUMMARY
Phase | 5.5 — Document Generation Hub
Product Version | v0.5 (post v0.4 LLM Provider Hardening)
TDD Reference | Test_Plan_Strategy_Document_Hub_TDD_v0.1.docx
Estimated Effort | ~11.5 developer-days (~2.5 weeks solo / ~1.5 weeks parallel backend+frontend track)
Dependencies | v0.4 LLM Provider Hardening (TDD v0.3) — MODEL_REGISTRY for consistent provider dispatch
DB Change | Additive only — +testStrategy: Json? and +testPlan: Json? on Generation model. Non-breaking.
New endpoints | POST /api/generate/teststrategy/stream, POST /api/generate/testplan/stream
New prompt files | src/prompts/test-strategy.txt (ISO 29119-3, 8 sections), src/prompts/test-plan.txt (IEEE 829, 15 sections)
New frontend components | DocumentPreviewPanel, UnsavedBanner, ProjectsTab enhancement
New npm package (frontend only) | docx v9.7.1 (for client-side DOCX generation — Packer.toBlob())
PHASE SEQUENCE IN ROADMAP
Slot | Phase 1-2-3 → Phase 2.5 → Phase 3.5 → Phase 4.5 (covers Phase 4 + Phase 5) → Phase 5.5 (THIS) → Phase 6 Rank 1
Does NOT overlap with | Phase 2.5 (Document Security), Phase 3.5 (RBAC Bridge), Phase 4.5, Phase 6 Rank 1
Note | Phase 5 content is already included inside Phase4_5.xlsx. Phase 5.5 is the next clean slot.
KEY DESIGN DECISIONS (locked in TDD v0.1 — re-opening requires new TDD revision + re-sign-off)
D-01 | LLM output format | Structured JSON sections — single source-of-truth for preview, DOCX generation, and DB storage
D-02 | DOCX generation | Client-side only — Packer.toBlob() in browser. No server file-serving endpoint.
D-03 | PDF generation | window.print() with @media print CSS — zero new dependencies, browser native
D-04 | In-app preview | HTML render from JSON sections — no third-party viewer, no licensing, full design token integration
D-05 | Save in Project UX | Explicit gate — amber unsaved banner (not auto-save). Confirms before persisting to project history.
D-06 | Generation order | Test Strategy first (Step 5, after Enhancement), Test Plan last (Step 6, receives Strategy as context)
STANDARD COMPLIANCE
Test Strategy | ISO/IEC/IEEE 29119-3 aligned — 8 sections (scope, approach, environments, tools, risk, entry/exit criteria, metrics, roles)
Test Plan | IEEE 829 aligned — 15 sections (full IEEE 829 §4.1–§4.15 structure)

## Feature Breakdown
Phase 5.5 — Feature Breakdown (7 Features)
All features are in scope for v0.5. Features marked P1 are required for release. P2 features ship in the same release but are lower priority if time-constrained.
# | Feature | Scope Description | Priority | User Value | Standard / Approach | New Dependencies
F-01 | Test Strategy Generation | New SSE endpoint: synthesises requirements + enhancement → ISO/IEC/IEEE 29119-3-aligned strategy document in structured JSON (8 sections). Stored in Generation.testStrategy (Json?). | P1 — Critical | First document-class output in TraceLMs Cloud. Answers "how will we test this?" — the most common QA Lead question that TraceLMs has no answer for today. | ISO/IEC/IEEE 29119-3. Prompt file: src/prompts/test-strategy.txt | None (backend: existing SSE pattern)
F-02 | Test Plan Generation | New SSE endpoint: synthesises ALL 6 prior artifacts + Test Strategy → IEEE 829-aligned test plan in structured JSON (15 sections). Receives Test Strategy as context. Stored in Generation.testPlan (Json?). | P1 — Critical | IEEE 829 Test Plan is the primary deliverable for enterprise QA teams with formal compliance requirements. Most-requested TraceLMs feature to date. | IEEE 829. Prompt file: src/prompts/test-plan.txt | None (backend: existing SSE pattern)
F-03 | In-App Document Preview Panel | DocumentPreviewPanel React component: section-by-section HTML render from stored JSON sections. Sticky section navigation sidebar (collapses at < 700px). Full-screen expand modal with ESC close. @media print CSS in styles.css. | P1 — Critical | Users review document content before downloading. Essential for quick verification and sharing screenshots in Slack/email without opening Word. | Zero new npm packages. CSS design tokens only. | None
F-04 | DOCX Download (client-side) | docxGenerator.ts utility: takes document JSON sections as input, generates a DOCX via docx npm v9.7.1 Packer.toBlob(). Downloads via URL.createObjectURL() + programmatic anchor click. Tested in Word, LibreOffice, Google Docs. | P1 — Critical | Offline copy for QA leads to share with project managers, store in SharePoint, or attach in Jira tickets. Enterprise QA requirement. | docx npm v9.7.1 (dual CJS/ESM, browser-compatible, confirmed via npm registry 2026-06-26) | docx v9.7.1 (frontend only)
F-05 | PDF Download (browser print) | window.print() called on the DocumentPreviewPanel element. @media print CSS: page-break-before: always on H1 section headings, clean layout, readable at 100% zoom. Tested Chrome, Edge, Firefox. | P2 — High | PDF required for formal review sign-off in many enterprise QA processes. Zero-dependency approach avoids Puppeteer overhead and ESM-only pdf libraries. | window.print() — browser native. @media print CSS scoped to .document-preview-panel | None
F-06 | "Save in Project" UX | UnsavedBanner component: amber "unsaved" state with project dropdown (GET /api/projects), green "saved" state with project link. PATCH /api/generations/:id sets projectId. Inline "Create new project" 2-field form. | P1 — Critical | Without this, generated documents are lost when the browser is closed. First proper generation persistence UX for TraceLMs Cloud. | PATCH /api/generations/:id (existing endpoint, adds projectId support) | None
F-07 | Project Artifact Consolidation View | ProjectsTab.tsx enhancement: project detail view → generation list with date/model/artifact-count → 6 artifact-presence chips per generation → expandable artifact cards → "Export Project Pack" DOCX (all 6 artifacts as one bookmarked DOCX). Reuses DocumentPreviewPanel and docxGenerator.ts. | P2 — High | QA leads can view all artifacts for a release in one place. "Export Project Pack" replaces the need to download each artifact individually. | Reuses F-03 (DocumentPreviewPanel) and F-04 (docxGenerator.ts) | None (reuses F-04 dependency)

## Implementation Tasks
Phase 5.5 — Implementation Tasks (8 Tasks)
T-01 and T-02 have no dependencies — can start immediately in parallel. T-03 and T-04+ can run as a backend/frontend parallel track after T-01/T-02 complete.
Task ID | Title | Full Description | Files Affected | Effort (days) | Depends On | Parallel Track | Status
T-01 | DB Schema Migration | Add testStrategy: Json? and testPlan: Json? to the Generation model in prisma/schema.prisma. Run npm run db:migrate to generate a new timestamped migration file. Verify that all existing Generation records are unaffected (both fields default to null). Run npm run typecheck to confirm Prisma client types regenerated correctly. | prisma/schema.prisma, prisma/migrations/ | 0.5 | None | Backend | Not started
T-02 | LLM Prompt Files | Write src/prompts/test-strategy.txt (8 sections, ISO/IEC/IEEE 29119-3 aligned). Write src/prompts/test-plan.txt (15 sections, IEEE 829 §4.1–§4.15 aligned). Both files must include JSON-only output instruction verbatim: "Respond ONLY with valid JSON. Do not wrap in markdown code fences. Do not add any prose outside the JSON object. Begin your response with { and end with }." Run npm run validate:prompts — both must pass. | src/prompts/test-strategy.txt, src/prompts/test-plan.txt | 1.0 | None | Backend | Not started
T-03 | Backend Endpoints | Add /api/generate/teststrategy/stream and /api/generate/testplan/stream route handlers to src/routes/generate.ts. Follow the identical SSE pattern established by /api/generate/scenarios/stream: loadPrompt() → callLLMStream() → extractJson() → prisma.generation.update(). Persist testStrategy to Generation.testStrategy and testPlan to Generation.testPlan after extractJson() succeeds. Reuse sseWrite(), sseError(), sseDone() helpers. Idle timeout: IDLE_MS = 300_000. | src/routes/generate.ts, src/types/index.ts | 1.5 | T-01, T-02 | Backend | Not started
T-04 | Frontend API Client | Add generateTestStrategy(params) and generateTestPlan(params) functions to frontend/src/api/client.ts — return EventSource instances following the same pattern as generateScenarios() and generateTestCases(). Update useTraceLMMessages.ts hook to handle SSE events from both new endpoints and update state. Add testStrategy: DocumentJson ¦ null and testPlan: DocumentJson ¦ null to the Generation type in frontend/src/types.ts. | frontend/src/api/client.ts, frontend/src/hooks/useTraceLMMessages.ts, frontend/src/types.ts | 1.0 | T-03 | Frontend | Not started
T-05 | Document Preview Panel | Build frontend/src/components/DocumentPreviewPanel.tsx: renders sections[].heading as H1, subsections as H2, sections[].content as body paragraphs, sections[].table as a styled HTML table. Includes a sticky left sidebar listing all section headings with active-section highlight. Full-screen expand modal (fixed overlay, fills viewport, ESC to close, no data loss). Add .document-preview-panel @media print CSS to frontend/src/styles.css: page-break-before: always on h1 section headings, no fixed-height containers, clean margins. Zero new npm packages. All styling via TraceLMs design tokens. | frontend/src/components/DocumentPreviewPanel.tsx, frontend/src/styles.css | 2.0 | T-04 | Frontend | Not started
T-06 | DOCX Download Utility | Add docx v9.7.1 to frontend/package.json (npm install docx). Add "docx" to optimizeDeps.include in vite.config.ts to force Vite pre-bundling and avoid ESM/CJS tree-shaking issues. Build frontend/src/utils/docxGenerator.ts: accepts a DocumentJson (sections[] from the stored JSON), constructs a docx Document with proper Heading1/Heading2 styles, US Letter page size (12240x15840 DXA), 1-inch margins, and numbered sections. Export via Packer.toBlob() → URL.createObjectURL() → programmatic <a download="filename.docx"> click → revokeObjectURL(). Test download opens correctly in: Microsoft Word, LibreOffice Writer, Google Docs (all sections present, headings in nav). | frontend/package.json, vite.config.ts, frontend/src/utils/docxGenerator.ts | 1.5 | T-04 | Frontend | Not started
T-07 | "Save in Project" UX | Build frontend/src/components/UnsavedBanner.tsx: amber bar with "This generation is unsaved. [Save to Project ▾]" text. Project dropdown fetches from GET /api/projects, shows project name + status badge. "Create new project" option at bottom of dropdown opens a 2-field inline form (Project Name, Owner); on submit: POST /api/projects then immediately PATCH /api/generations/:id with new projectId. On project selection: PATCH /api/generations/:id with { projectId }, banner transitions to green "Saved to [Project Name] ✓ · [View Project →]" state. × button dismisses amber banner for session (does not save — re-appears on reload if still unsaved). | frontend/src/components/UnsavedBanner.tsx, frontend/src/api/client.ts | 1.5 | T-04 | Frontend | Not started
T-08 | Project Consolidation View | Enhance frontend/src/tabs/ProjectsTab.tsx with a project detail view: clicking a project card enters a detail view showing all saved generations sorted by date descending. Each generation row shows: date, LLM model, # requirements, # test cases, # scenarios, and 6 artifact-presence chips (filled teal = generated, outline = missing) for: Enhancement, Scenarios, Test Cases, Automation, Test Strategy, Test Plan. Clicking an artifact chip expands inline to show the full artifact content (reuse existing renderers for table-based artifacts; use DocumentPreviewPanel for Test Strategy and Test Plan). "Export Project Pack" button: calls docxGenerator.ts with all 6 artifact sections merged into one DOCX with bookmarked H1 section headings. E2E test: generate all 6 artifacts → save to project → view in Projects tab → expand artifact cards → export pack → open DOCX in Word. | frontend/src/tabs/ProjectsTab.tsx, frontend/src/components/ | 2.5 | T-05, T-06, T-07 | Frontend | Not started
|  | Total estimated effort |  | 11.5 days
PARALLEL TRACK RECOMMENDATION
Track | Tasks | Days | Notes
Backend engineer | T-01 → T-02 → T-03 (sequential) | 3.0 days | Can start Day 1. Unblocks frontend T-04 on Day 3.
Frontend engineer | T-01 awareness → T-04 → T-05 → T-06 → T-07 → T-08 | 8.5 days total; T-04 starts Day 3 when T-03 ready | T-05, T-06, T-07 can partially overlap after T-04 complete.
Parallel wall-clock time | ~8–9 days (~1.5 weeks) |  | Backend finishes Day 3; Frontend finishes Day 9–10.

## Acceptance Criteria
Phase 5.5 — Acceptance Criteria (13 Items)
All P1 ACs must pass before release. P2 ACs must pass before close of sprint.
AC ID | Feature | Criterion | Pass Condition | Priority
AC-01 | Test Strategy generation | /api/generate/teststrategy/stream returns valid JSON with all 8 required section IDs | extractJson() succeeds on first strategy (direct JSON.parse); all 8 section IDs present in response body | P1
AC-02 | Test Strategy generation | Test Strategy content is derived from the requirements and enhancement of the same generation session | Section 2 (Test Scope) references feature names from the enhancement output of the same generation | P1
AC-03 | Test Plan generation | /api/generate/testplan/stream returns valid JSON with all 15 IEEE 829 section IDs | extractJson() succeeds; all 15 section IDs present; section 6 (Approach) explicitly references the Test Strategy | P1
AC-04 | Test Plan generation | Test Plan and Test Strategy are internally consistent | Test Plan section 6 (Approach) references methodology from the Test Strategy generated in the same session | P1
AC-05 | Document Preview Panel | DocumentPreviewPanel renders all sections with correct heading hierarchy | H1 for section headings, H2 for sub-headings, body text for content — matches section JSON structure exactly | P1
AC-06 | Document Preview Panel | Section navigation sidebar links scroll to the correct section | Clicking a link scrolls the panel to that section; the clicked section heading is highlighted as active | P1
AC-07 | DOCX download | Downloaded DOCX opens without error in Microsoft Word | File opens, all sections present, no rendering errors, headings visible in Word's built-in Navigation Panel | P1
AC-08 | DOCX download | DOCX content matches in-app preview exactly | All section headings and body text in the DOCX match the DocumentPreviewPanel render (no missing or reordered sections) | P1
AC-09 | PDF download | window.print() renders a clean print preview with page breaks | Each major section starts on a new page; all text readable at 100% zoom; no content clipped in Chrome, Edge, Firefox | P2
AC-10 | Save in Project | Amber unsaved banner appears within 1s after every generation step completes | Banner visible within 1 second of SSE stream completion for Enhancement, Test Strategy, and Test Plan | P1
AC-11 | Save in Project | PATCH /api/generations/:id sets projectId correctly | After project selection: GET /api/generations/:id returns updated projectId; banner transitions to green "Saved" state | P1
AC-12 | Project Consolidation | Project detail shows all generations saved to that project | Saved generation appears in project detail within 2 seconds of save; shows date, model, artifact presence chips | P2
AC-13 | Project Consolidation | "Export Project Pack" DOCX contains all 6 artifact types as bookmarked sections | DOCX contains 6 bookmarked H1 headings; each contains the full content of its artifact type; opens in Word without error | P2

## Risk Register
Phase 5.5 — Risk Register (5 Risks)
Risk ID | Risk | Likelihood | Impact | Mitigation
R-01 | Test Plan context window overflow — synthesising 6 artifact types may exceed model context limits for large requirement sets or smaller models (e.g. claude-haiku-4-5 at 200k context, large automation batch output) | Medium | High | Set PLAN_MAX_TOKENS guard in test-plan.txt prompt: truncate automation candidates first (lowest information density per token). Add soft-block UI warning if estimated total input chars > 80k. Test against claude-haiku-4-5 (200k context) and claude-opus-4-8 (1M context) with a 50-requirement set.
R-02 | docx npm Vite bundler compatibility — docx v9.7.1 is dual CJS/ESM but Vite tree-shaking may produce unexpected bundle issues when imported in the browser context | Low | Medium | Add to vite.config.ts: optimizeDeps: { include: ['docx'] } to force Vite pre-bundling. Run npm run build:frontend immediately after adding the package (before any feature code). Fall back to dynamic import() if build errors occur.
R-03 | window.print() @media print CSS cross-browser inconsistency — print rendering differs between Chrome, Firefox, and Edge, particularly for page-break-before and fixed-position elements | Medium | Low | Use page-break-before: always on H1 section headings (not page-break-inside: avoid). Avoid fixed-height containers and position: fixed elements in @media print rules. Test all three browsers during T-05 before marking complete.
R-04 | LLM JSON non-compliance — LLM occasionally outputs prose or markdown code fences instead of pure JSON for the document sections, causing extractJson() to fall to strategy 2 or 3 | Low | Medium | extractJson() already handles markdown fences and partial JSON via 3-strategy extraction. Prompt explicitly instructs JSON-only output. Add an integration smoke test: send a minimal 3-requirement set through both endpoints and verify extractJson() success on the first strategy (direct JSON.parse) over 5 consecutive runs.
R-05 | Project selector empty state — new users with no projects see an empty project dropdown and may not discover the "Create new project" option | Medium | Low | Show "Create new project" as the FIRST item (not last) in the dropdown when the project list is empty. Add an empty-state illustration with CTA text ("No projects yet. Create your first →") inside the dropdown panel when GET /api/projects returns an empty array.

## Roadmap Context
Phase Roadmap Context — Where Phase 5.5 Sits
Phase | File | Content | Status
Phase 1-2-3 | TraceLMs_Cloud_Implementation_Plan_Phase1_2_3.xlsx | Core platform — Auth, Storage, Requirements Tab | Complete
Phase 2.5 | TraceLMs_Cloud_Implementation_Plan_Phase2_5_Document_Security_v0.2.xlsx | Document Security Gateway — 8-step validation pipeline, PromptSanitizer, ZIP bomb protection | DRAFT — Pending sign-off
Phase 3.5 | TraceLMs_Cloud_Implementation_Plan_Phase3_5_RBAC_Bridge.xlsx | RBAC Bridge — role-based access control | Status unknown — check file
Phase 4.5 | TraceLMs_Cloud_Implementation_Plan_Phase4_5.xlsx | Covers Phase 4 AND Phase 5 content | Status unknown — check file
Phase 5.5 (THIS) | TraceLMs_Cloud_Implementation_Plan_Phase5_5_Document_Hub.xlsx | Document Generation Hub — Test Plan, Test Strategy, Preview, Download, Save in Project, Consolidation View | DRAFT — Pending TDD sign-off
Phase 6 | TraceLMs_Cloud_Implementation_Plan_Phase6_Rank1.xlsx | Rank 1 features — document templates, branding, Jira/Xray Test Plan push | Status unknown — check file
FEATURE DEPENDENCY NOTE
Phase 5.5 F-03 (Preview) and F-04 (DOCX download) are REUSED by F-07 (Project Consolidation View). Build F-03 and F-04 first (T-05, T-06) before building T-08.
Phase 6 branding/templates feature is explicitly OUT OF SCOPE for Phase 5.5. It is already in Phase6_Rank1.xlsx. Do not add templating to Phase 5.5 implementation.
SIGN-OFF REQUIRED BEFORE IMPLEMENTATION
Role | Name | Date | Approved?
PM / CTO
Engineering Lead
QA Lead