## Slide 1
TraceLMs Cloud
Phase 4 & 5
Implementation Plan
AI Quality & Market Differentiators
v0.1.0
June 24, 2026
51 Tasks
2 Phases
Prepared for: Directors · Delivery Head · Product Managers · Country Head

## Slide 2
Executive Summary
Strategic value delivered by Phase 4 and Phase 5
Phase 4
AI Quality & Prompt Management
24 tasks · 13 High Priority · ~5 weeks
Unlocks in-browser prompt editing, AI quality scoring,
user feedback loops, version control, and inline test editing.
Gives QA teams direct control over LLM output quality.
Phase 5
Market Differentiators
27 tasks · 21 High Priority · ~10 weeks
Bi-directional traceability, RAG-powered search, regression
impact analysis, multi-language test output, analytics dashboard,
and bulk operations — features no direct competitor offers today.
Impact
Combined Strategic Outcome
51 total tasks across both phases.
Transforms TraceLMs Cloud from a generator into an AI-native
QA platform with full traceability, quality governance,
and market-differentiating intelligence.
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
2

## Slide 3
Portfolio at a Glance
Phase 4 & 5 — combined task breakdown
51
Total Tasks
34
High Priority
14
Medium Priority
24
Small Effort
 | Total Tasks | High Priority | Medium Priority | Low Priority | Small Effort | Timeline
Phase 4 — AI Quality | 24 | 13 | 9 | 2 | 17 | ~5 weeks
Phase 5 — Differentiators | 27 | 21 | 5 | 1 | 7 | ~10 weeks
TOTAL | 51 | 34 | 14 | 3 | 24 | ~15 weeks
High
Medium
Low
Priority legend
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
3

## Slide 4
PHASE 4
AI Quality &
Prompt Management
5 features · 24 tasks · ~5 weeks · Foundation for AI quality governance
Prompt Management UI
AI Quality Scoring
User Feedback Loop
Prompt Version Control
Inline Test Case Editing

## Slide 5
Phase 4 · Feature 1: Prompt Management UI
In-browser prompt editing — Week 1–2 · High Priority · 6 tasks
Task | Description | Effort | Timeline | Status
Prisma PromptTemplate model | Add DB model for prompt templates per step (enhancement/scenarios/testcases/automation). Seed with current .txt contents. | Small | Week 1 | To Do
GET /api/prompts route | Returns all prompt templates grouped by step. Supports ?step= query param. Returns id, name, step, isDefault, isActive. | Small | Week 1 | To Do
PUT /api/prompts/:id route | Updates content of a prompt template. Validates step enum. Returns updated record. | Small | Week 1 | To Do
POST /api/prompts/reset/:id | Resets a template to its seed default (reads original .txt). Prevents loss of baseline prompt. | Small | Week 1 | To Do
Prompt editor component | Frontend: CodeMirror-based editor in a new Prompts tab. Shows step selector, active/default toggles, Save and Reset buttons. | Medium | Week 1–2 | To Do
Active prompt indicator | Generation pipeline reads active prompt from DB instead of .txt file. Shows which prompt version is active per step. | Small | Week 2 | To Do
Business Value: QA teams can tune LLM prompts without engineering involvement — reducing iteration cycles from days to minutes.
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
5

## Slide 6
Phase 4 · Features 2 & 3: AI Quality Scoring & Feedback Loop
Week 2–4 · High Priority · 9 tasks
Feature | Task | Description | Effort | Status
AI Quality Scoring | QualityScore Prisma model | Stores score, rationale, breakdown (completeness/clarity/coverage) per generation. | Small | To Do
 | POST /api/generate/score | Sends test cases to LLM scorer. Returns 0–10 score with per-dimension breakdown. | Medium | To Do
 | Quality score display | Score badge and radar chart in Test Cases tab. Red/amber/green threshold indicators. | Medium | To Do
 | Quality threshold enforcement | Block Xray push if score < configurable threshold. Prompts user to regenerate. | Medium | To Do
 | Score history analytics | Score trend chart over time. Highlights prompt changes that improved/degraded quality. | Large | To Do
Feedback Loop | Feedback Prisma model | Stores per-test-case thumbs up/down + optional comment. Links to generation and prompt version. | Small | To Do
 | Thumbs up/down UI | Inline rating on each test case card. One click — no modal. | Small | To Do
 | Feedback analytics dashboard | Aggregated feedback scores per prompt version. Shows which prompt changes drove improvement. | Medium | To Do
 | Feedback-driven tuning suggestions | AI suggests prompt edits based on low-scored test cases. Highlights patterns in negative feedback. | Large | To Do
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
6

## Slide 7
Phase 4 · Features 4 & 5: Prompt Version Control & Inline Editing
Week 4–5 · Medium–High Priority · 6 tasks
Feature | Task | Description | Effort | Status
Prompt Version Control | PromptVersion model | Records each save as a version: id, promptId, content, savedBy, createdAt. Immutable history. | Small | To Do
 | Version diff viewer | Side-by-side diff of any two versions. Highlights added/removed lines. Accessible from version history panel. | Medium | To Do
 | Rollback to previous version | One-click restore. Sets prior version content as active. New version entry created on rollback. | Small | To Do
Inline Test Case Editing | Editable test case fields | Click-to-edit title, steps, expected results, and labels directly in the Test Cases tab. Auto-saves with debounce. | Medium | To Do
 | Edit history / change tracking | Records each edit: field, old value, new value, timestamp, user. Visible in a 'History' drawer per test case. | Medium | To Do
 | Re-push edited test case to Xray | Button to push updated test case to Xray after editing. Updates existing Xray test key — no duplicate. | Small | To Do
Phase 4 Complete: 24 tasks · 5 features · ~5 weeks · Unlocks AI quality governance and prompt ownership for QA teams
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
7

## Slide 8
PHASE 5
Market
Differentiators
6 features · 27 tasks · ~10 weeks · Capabilities no direct competitor offers today
Bi-dir Traceability
Regression Impact
RAG Indexing
Multi-lang Output
Analytics Dashboard
Bulk Operations

## Slide 9
Phase 5 · Feature 1: Bi-directional Requirement Traceability
FLAGSHIP FEATURE · Week 1–3 · High Priority · 4 tasks
Task | Description | Effort | Timeline | Risk | Status
RequirementClause model | Stores extracted clauses from requirement text: id, generationId, index, text, hash. Generated server-side on requirement submission. | Medium | Week 1–2 | Low | To Do
POST /api/generate/trace-map | Sends requirements + test cases to LLM. Returns mapping: { testCaseId → requirementClauseIndices[] }. Uses a dedicated traceability prompt. | Medium | Week 2 | High | To Do
Traceability matrix view | Toggle in TestCases tab: Card View ↔ Traceability Matrix. Requirement clauses as rows, test cases as columns. Exportable as CSV. | Large | Week 3 | Medium | To Do
Stale test case detection | When requirements change, hash-compare old vs new clauses. Flag test cases linked to changed clauses as 'Stale — requirement changed.' | Medium | Week 3 | Medium | To Do
Risk: LLM hallucination risk on trace-map route — LLM may map test cases to incorrect clauses. Mitigation: confidence scoring + human review toggle before accepting mappings.
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
9

## Slide 10
Phase 5 · Features 2 & 3: Regression Impact Analysis & RAG Indexing
Week 3–7 · High Priority
Feature | Task | Description | Effort | Timeline | Status
Regression Impact Analysis | Diff engine | Text diff of old vs new requirement versions. Identifies added, removed, and modified clauses. | Medium | Week 3 | To Do
 | Impact scoring route | POST /api/generate/impact — scores which test cases are at risk based on changed clauses. | Medium | Week 4 | To Do
 | Change Impact panel in UI | Side panel in TestCases tab listing impacted test cases with risk level and change summary. | Medium | Week 4–5 | To Do
 | Jira change detection webhook | Subscribe to Jira issue_updated events. Auto-trigger impact analysis when linked Jira ticket changes. | Large | Week 5 | To Do
RAG Requirement Indexing | Vector embedding pipeline | Embed each requirement clause using OpenAI/Gemini embeddings. Store vectors in Supabase pgvector. | Medium | Week 5–6 | To Do
 | pgvector Supabase integration | Enable pgvector extension. Cosine similarity search on requirement vectors for semantic retrieval. | Small | Week 5 | To Do
 | Semantic search route | GET /api/requirements/similar — returns top-5 semantically similar requirement sets for the current input. | Small | Week 6 | To Do
 | 'Similar requirements' panel | Suggestions panel in Requirements tab showing related past requirements. One click to load as template. | Medium | Week 7 | To Do
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
10

## Slide 11
Phase 5 · Features 4 & 5: Multi-language Output & Analytics Dashboard
Week 7–10 · Medium–High Priority
Feature | Task | Description | Effort | Timeline | Status
Multi-language Test Output | Language selector per test case | Dropdown on each test case: Gherkin (default), Jest, Pytest, JUnit, Cypress, Playwright. Preserves original Gherkin. | Small | Week 7 | To Do
 | Code generation prompt templates | Dedicated prompt template per target language. Translates Gherkin steps into executable code. | Medium | Week 7–8 | To Do
Analytics & Reporting | Generation metrics aggregation | DB view: generations per day/week, avg quality score, push success rate, top LLM providers used. | Medium | Week 8 | To Do
 | Analytics dashboard page | New Analytics tab: charts for generation volume, quality trends, provider usage, push rates. | Large | Week 8–9 | To Do
 | Exportable PDF/Excel reports | Download generation summary as PDF or Excel. Includes quality scores, traceability matrix, push history. | Medium | Week 9 | To Do
 | Jira coverage dashboard embed | Jira macro (gadget) that shows requirement coverage % for a project. Pulls from TraceLMs Cloud API. | Large | Week 9–10 | To Do
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
11

## Slide 12
Phase 5 · Feature 6: Bulk Operations
Week 9–10 · High Priority · 4 tasks
Task | Description | Effort | Timeline | User Impact | Status
Multi-select test cases | Checkbox selection on all test case cards. Select All / Deselect All. Count badge shows selected items. | Small | Week 9 | Foundation for all bulk ops | To Do
Bulk Xray push | Push all selected test cases to Xray in one operation. Progress bar and per-item success/fail status. | Medium | Week 9 | Eliminates repetitive single-push workflow | To Do
Bulk export (CSV/Excel) | Export selected test cases as CSV or formatted Excel. Includes all fields: title, steps, expected, labels, status. | Small | Week 9–10 | QA leads can share test suites externally | To Do
Bulk status update | Update status (Draft/Ready/Reviewed/Approved) on all selected test cases simultaneously. Audit-logged. | Small | Week 10 | Reduces review overhead by 80% | To Do
Phase 5 Complete: 27 tasks · 6 features · ~10 weeks · Traceability, RAG, regression detection, multi-language output, analytics, and bulk ops
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
12

## Slide 13
Delivery Timeline
Phase 4 & 5 — 15-week combined roadmap
Chart: 
| P4: Prompt Mgmt UI | P4: AI Quality Scoring | P4: Feedback Loop | P4: Version Control | P4: Inline Editing | P5: Traceability | P5: Regression Impact | P5: RAG Indexing | P5: Multi-lang Output | P5: Analytics Dashboard | P5: Bulk Operations
Start | 0 | 1 | 2 | 3 | 4 | 0 | 2 | 4 | 6 | 7 | 8
Phase 4 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Phase 5 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 2 | 3 | 2
Weeks 1–15 (each bar unit = 1 week)
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
13

## Slide 14
Risk Summary
Key risks across Phase 4 & 5 with mitigations
ID | Severity | Phase | Risk | Mitigation
R1 | High | Phase 5 | LLM hallucination on trace-map route | Add confidence scoring. Require human review toggle before accepting mappings. Start with rule-based fallback.
R2 | Medium | Phase 4 | Invalid prompt content breaks generation pipeline | Validate prompt syntax on save. Dry-run prompt against test input before activating. Rollback available.
R3 | Medium | Phase 5 | Traceability matrix performance with 50+ test cases | Implement row/column virtualization. Paginate matrix beyond 50 items. Add export as CSV fallback.
R4 | Medium | Phase 5 | RAG embedding quality depends on LLM embedding model | Benchmark OpenAI vs Gemini embeddings on internal requirement sets. Use cosine similarity threshold filter.
R5 | Low | Phase 4 | Score history analytics adds DB query load | Add DB index on generationId + createdAt. Use a materialized view for aggregated analytics queries.
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
14

## Slide 15
Success Metrics
How we measure the impact of Phase 4 & 5
Phase 4
✓ Prompt edit-to-activation time < 2 min (vs engineering ticket: 2 days)
✓ AI quality score avg ≥ 7.5/10 within 2 weeks of scoring launch
✓ Positive user feedback rate ≥ 70% on scored test cases
✓ Zero prompt-loss incidents (version rollback available)
Phase 5
✓ 100% of generated test cases traceable to a requirement clause
✓ Stale test detection accuracy ≥ 90% on requirement changes
✓ RAG semantic search latency < 1s for 95th percentile
✓ Analytics dashboard adoption: used by ≥ 80% of active projects
Combined
✓ QA engineer time-to-test-case: reduce from 3h → 20min
✓ Xray push success rate ≥ 98% across bulk operations
✓ NPS improvement of +15 points after Phase 5 launch
✓ Zero regression in existing Phase 1–3 features
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026
15

## Slide 16
Next Steps & Leadership Asks
What we need to move from Plan to Execution
01
Approve Phase 4 & 5 scope and timeline
Sign off on the 51-task scope. Confirm 15-week delivery window is acceptable given current team capacity.
02
Allocate engineering capacity
Phase 4 requires 1 backend + 1 frontend engineer full-time for 5 weeks. Phase 5 requires 2 backend + 1 frontend for 10 weeks.
03
Prioritize traceability as flagship feature
Bi-directional traceability (Phase 5, Feature 1) is a market-differentiating capability. Confirm it stays at top priority.
04
Approve RAG infrastructure cost
pgvector on Supabase Pro plan required. Embedding API calls add ~$0.002/requirement set. Budget approval needed.
05
Define quality score threshold policy
What is the minimum acceptable AI quality score before a test case can be pushed to Xray? Suggested: 6.5/10.
TraceLMs Cloud · v0.1.0 · Confidential · June 24, 2026