## Slide 1
TraceLMs Cloud
Phase 6:
Rank-1 Strategy
Target: 9.6 / 10 · Rank 1
44 Tasks
6 Pillars
14 Weeks
v0.1.0 Base
Product Depth
Enterprise
Ecosystem
AI Innovation
Brand & GTM
Community
Prepared for: Directors · Delivery Head · Product Managers · Country Head

## Slide 2
Executive Summary
The case for Rank-1 — what it means and why it matters now
9.6 / 10
Target Score
44
Tasks
6
Pillars
14
Weeks
June 24, 2026
What Phase 6 Achieves
Closes the end-to-end gap between requirement and executed, traced, and validated test — in one platform. No competitor does this today.
Why Rank 1 Matters
A 9.6/10 product score unlocks Atlassian Marketplace listing, SOC 2 certification, enterprise sales, and a defensible category leadership position.
Strategic Sequencing
6 pillars execute in parallel: Product Depth (run tests in CI), Enterprise Readiness (SOC 2/SSO), Ecosystem (API + Jira native), AI Innovation (custom model), Brand/GTM (freemium + marketing), Community (open source + docs).
Investment Required
Engineering, infrastructure, and go-to-market resources across 14 weeks. Leadership decisions needed on SOC 2 engagement, Stripe pricing, and open-source IP policy.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
2

## Slide 3
The 6 Pillars to Rank 1
Each pillar addresses a distinct dimension of product excellence
Product Depth
8
Tasks
4
Critical
3
Rank★
1–12
Weeks
Test execution runner, CI/CD integration, advanced export — closes the end-to-end product gap.
Enterprise Readiness
8
Tasks
4
Critical
4
Rank★
1–10
Weeks
SOC 2 Type II, SSO/SAML 2.0, SCIM provisioning, advanced RBAC.
Ecosystem & Integrations
8
Tasks
5
Critical
5
Rank★
2–14
Weeks
Public REST API, Atlassian Marketplace, webhooks, Azure DevOps, SDK packages.
AI Innovation
7
Tasks
3
Critical
3
Rank★
1–13
Weeks
Fine-tuned TraceLMs-QA model, autonomous test maintenance, multi-modal input.
Brand & GTM
7
Tasks
4
Critical
3
Rank★
1–14
Weeks
Freemium tier, Stripe billing, marketing site, LLM benchmark authority, content programme.
Community & Trust
6
Tasks
3
Critical
3
Rank★
3–10
Weeks
Open-source core, developer docs site, TypeScript/Python SDKs, partner programme.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
3

## Slide 4
Pillar Summary Dashboard
44 total tasks · 23 critical · 21 rank-defining · 14-week execution
Pillar | Total Tasks | Critical | High | Rank-Defining | Timeline | Key Deliverable
Product Depth | 8 | 4 | 2 | 3 | Weeks 1–12 | Playwright test runner + CI/CD API
Enterprise Readiness | 8 | 4 | 3 | 4 | Weeks 1–10 | SOC 2 Type II + SSO/SAML 2.0
Ecosystem & Integrations | 8 | 5 | 1 | 5 | Weeks 2–14 | Atlassian Marketplace + Public API
AI Innovation | 7 | 3 | 3 | 3 | Weeks 1–13 | Fine-tuned TraceLMs-QA model
Brand & GTM | 7 | 4 | 2 | 3 | Weeks 1–14 | Freemium + Stripe + Marketing site
Community & Trust | 6 | 3 | 2 | 3 | Weeks 3–10 | Open-source core + Developer docs
TOTAL | 44 | 23 | 15 | 21 | 14 weeks | Rank-1 Product
Critical
Rank-defining
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
4

## Slide 5
Pillar 1
Product Depth — 8 tasks · Weeks 1–12 · 4 critical · 3 rank-defining
Feature | Task | Description | Priority | Effort | Impact | Status
Test Execution Runner | Playwright runner service | Backend service: POST /api/execute/run. Maps Gherkin steps to Playwright actions. Streams stdout/stderr via SSE. TestRun Prisma model. | Critical | Large | Rank-defining | To Do
 | Execution results UI | 'Run Tests' button in TestCases tab. Status pills: Not Run / Running / Pass / Fail / Error. Screenshot thumbnails on failure. | Critical | Medium | Rank-defining | To Do
CI/CD Integration | Public REST API endpoint | POST /api/v1/generate — API-key authenticated, async, 202 Accepted. Poll GET /api/v1/generation/:id. OpenAPI 3.1 spec at /api/v1/docs. | Critical | Medium | Rank-defining | To Do
 | GitHub Actions marketplace | tracelms-cloud/generate-tests action. Inputs: api-key, requirement-file, project-id, xray-push. Published to GitHub Marketplace. | Critical | Medium | Rank-defining | To Do
 | GitLab CI + Jenkins plugin | GitLab CI Catalog component. Jenkins .hpi plugin on Jenkins Plugin Index. Both wrap the same REST API. | High | Large | High | To Do
Advanced Export | XLSX + PDF + Confluence | Traceability-linked Excel export, PDF test report generation, Confluence page publish via REST API. | Medium | Small | Medium | To Do
Risk: Playwright→Gherkin step mapping is non-trivial. Start with structured Given/When/Then patterns and explicit selectors. Budget 4 weeks for the runner service alone. Do not promise NLP-based step mapping until V2.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
5

## Slide 6
Pillar 2
Enterprise Readiness — 8 tasks · Weeks 1–10 · 4 critical · 4 rank-defining
Feature | Task | Description | Priority | Effort | Timeline | Status
SOC 2 Type II | Security controls audit | Engage Vanta/Drata/Secureframe. Gap assessment against Trust Services Criteria. Document existing controls (AES-256-GCM, CORS, rate limiting). | Critical | Large | Week 1–2 | To Do
 | Audit trail + access logging | AuditLog model: id, userId, action, resourceType, ipAddress, userAgent, createdAt. Middleware on every auth'd API call. GET /api/admin/audit-log. | Critical | Medium | Week 2–3 | To Do
 | Vulnerability management | Snyk or Dependabot on every PR. npm audit in CI (fail-on-high). SLA policy: critical 24h, high 7 days, medium 30 days. | Critical | Small | Week 2 | To Do
SSO / SAML 2.0 | SAML 2.0 + OIDC integration | passport-saml + openid-client in Express. Supports Okta, Azure AD, Google Workspace, OneLogin. JIT user provisioning. Fallback email/password login. | Critical | Large | Week 3–6 | To Do
 | SCIM 2.0 provisioning | GET/POST/PATCH/DELETE /scim/v2/Users. Auto-provision/deprovision users from IdP. Required by Okta + Azure AD enterprise integrations. | High | Large | Week 6–8 | To Do
Advanced RBAC | Role expansion + matrix | Roles: Owner/Admin/Editor/Viewer/Guest. Permission matrix enforcement on all API routes. Org-level audit dashboard. | High | Medium | Week 2–5 | To Do
Note: SOC 2 Type II requires a 6–12 month observation period. Starting the audit engagement in Week 1 is mandatory — any delay directly extends the certification timeline.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
6

## Slide 7
Pillar 3
Ecosystem & Integrations — 8 tasks · Weeks 2–14 · 5 critical · 5 rank-defining
Feature | Task | Description | Priority | Effort | Impact | Status
Public REST API | API key management | Org admins create/rotate/revoke API keys. Prefixes: tlm_live_ / tlm_test_. Hashed (bcrypt). Scopes: generate, xray:push, admin. Usage stats per key. | Critical | Medium | Rank-defining | To Do
 | Webhook system | Org-configurable webhooks: generation.completed/failed, xray.pushed. HMAC-SHA256 signature. Exponential backoff (3 retries). Delivery log in settings. | Critical | Medium | Rank-defining | To Do
 | OpenAPI 3.1 docs site | Auto-generate from Express routes (tsoa or zod-openapi). Serve at /api/v1/docs (Scalar or Redoc). Code examples: TypeScript, Python, curl. | Critical | Small | Rank-defining | To Do
Atlassian Marketplace | Atlassian Connect app | atlassian-connect.json descriptor. OAuth 2.0 3LO (three-legged) — replaces Basic Auth. Jira issue panel showing generation status. Required for Marketplace listing. | Critical | Large | Rank-defining | To Do
 | 'Generate tests' Jira action | One-click on Jira ticket: sends summary + description + AC to generation pipeline. Results in issue panel. One-click Xray push. No context switching. | Critical | Large | Rank-defining | To Do
More Integrations | Azure DevOps + TestRail + Zapier | Azure DevOps Test Plans integration (High). TestRail integration (Medium). Zapier/Make/n8n native app (Medium). All via OpenAPI client gen. | High | Large | High | To Do
Note: Atlassian partner review takes 4–6 weeks. Submit the Connect app manifest no later than Week 7 to avoid delays to the Marketplace listing target date.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
7

## Slide 8
Pillar 4
AI Innovation — 7 tasks · Weeks 1–13 · 3 critical · 3 rank-defining
Feature | Task | Description | Priority | Effort | Timeline | Status
Fine-Tuned Model | Training data pipeline | Export anonymised JSONL pairs (generationId, requirementText, testCases) with feedbackScore ≥ 4. PII scrubbing (regex + NER). Target: 10,000+ pairs. Store in Supabase Storage. | Critical | Large | Week 1–4 | To Do
 | Fine-tune Llama 3 / Mistral | LoRA/QLoRA fine-tuning on GPU cloud (Lambda Labs or Modal). Eval: BLEU on Gherkin output, completeness score, human eval by QA engineers. Target: outperform GPT-4o-mini at 1/10th cost. | Critical | Large | Week 6–10 | To Do
 | Model serving + integration | Deploy via Together AI (managed) or vLLM (self-hosted). Add 'TraceLMs-QA' as 5th provider in LLMService.ts. Bundled in Pro plan. Publish benchmark results publicly. | Critical | Large | Week 10–12 | To Do
Autonomous Maintenance | Jira change webhook listener | Subscribe to Jira issue_updated events. Debounce 5 min. Auto-flag stale test cases on requirement change. Email + in-app notification to project owner. | High | Medium | Week 8–9 | To Do
 | Auto-suggest updated steps | On stale detection: 'Regenerate affected steps' action. Targeted LLM update — returns only changed steps. User reviews diff (old vs suggested). One-click re-push to Xray. | High | Large | Week 9–11 | To Do
Multi-Modal Input | Image/Voice ingestion | Image ingestion: screenshots, Figma exports, architecture diagrams (Week 9–12). Voice input: Whisper transcription → generation pipeline (Week 11–13). | Medium | Large | Week 9–13 | To Do
Risk: Fine-tuning quality is unpredictable without sufficient training volume. Do not announce a 'TraceLMs-QA model' until evaluation results confirm quality. Maintain GPT-4o fallback until model evaluation passes QA engineer review.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
8

## Slide 9
Pillar 5
Brand & GTM — 7 tasks · Weeks 1–14 · 4 critical · 3 rank-defining
Feature | Task | Description | Priority | Effort | Impact | Status
Freemium Tier | Free plan enforcement | Plan model: tier (FREE/PRO/ENTERPRISE), generationsUsed, generationsLimit (3 for FREE). Middleware gate. 402 on limit. Monthly counter reset. | Critical | Medium | Rank-defining | To Do
 | Stripe Billing integration | Stripe checkout for PRO plan. Webhook handler: subscription created/updated/cancelled/payment_failed. Update org tier on payment. In-app upgrade modal with feature comparison. | Critical | Large | Rank-defining | To Do
 | Marketing site + pricing page | Next.js/Astro site at tracelms.cloud. App at app.tracelms.cloud. Hero + demo video, feature grid, pricing table, ROI calculator, 'Book a demo' CTA for Enterprise. | Critical | Large | Rank-defining | To Do
Thought Leadership | LLM benchmark report | 50 requirement sets × 4 LLM providers × 5 metrics. Publish at tracelms.cloud/benchmark. Updated quarterly. Strongest SEO + trust-building content possible. | Critical | Medium | High | To Do
 | Content programme + SEO | Weekly: 1 technical deep-dive + 1 QA guide + benchmark update. Keywords: 'AI test case generation', 'Jira to Xray automation', 'Gherkin generator AI'. 6–12 month SEO compounding. | High | Small | High | To Do
Enterprise Sales | Sales deck + case studies | Enterprise sales deck with ROI calculator (Week 6–7, High). Case study programme: 3 design partners in Year 1 (Week 8–14, High). | High | Small | High | To Do
Insight: The LLM benchmark report is the single highest-leverage content piece — it establishes TraceLMs Cloud as the authority on AI test generation quality and attracts both enterprise buyers and developer community.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
9

## Slide 10
Pillar 6
Community & Trust — 6 tasks · Weeks 3–10 · 3 critical · 3 rank-defining
Feature | Task | Description | Priority | Effort | Impact | Status
Open Source Core | Extract @tracelms/core | Extract src/services/llm/, src/routes/generate.ts, src/prompts/, src/utils/ into @tracelms/core npm package. MIT license. Cloud platform remains proprietary. | Critical | Large | Rank-defining | To Do
 | GitHub community infra | CONTRIBUTING.md, CODE_OF_CONDUCT.md, issue/PR templates, GitHub Discussions. 48h first-response SLA for first 6 months. 2–3h/week community management. | Critical | Small | Rank-defining | To Do
Developer Docs | docs.tracelms.cloud site | Docusaurus or Mintlify. Sections: 5-min quickstart, REST API reference, webhooks, CI/CD guides (GitHub/GitLab/Jenkins), SDK reference, Prompt Engineering Guide, changelog. | Critical | Large | Rank-defining | To Do
 | TypeScript + Python SDKs | @tracelms/sdk → npm. tracelms-cloud → PyPI. Auto-generated from OpenAPI spec (openapi-generator or fern.dev). Full type safety, async/await, streaming support. | High | Medium | High | To Do
Partner Programme | QA consultancy partners | 30% recurring revenue share. White-label option (custom subdomain + logo). Co-marketing: partner logo on tracelms.cloud, joint case studies. Target: 10 partners in Year 1. | High | Medium | High | To Do
 | Certification programme | 'TraceLMs Certified QA Engineer' certification. Self-paced online course. Validates proficiency in AI-assisted QA workflows. Partner priority for certified engineers. | Medium | Large | Medium | To Do
Note: Open-sourcing requires a security review before any code is published. Confirm no credentials, proprietary algorithms, or customer data exist in the extraction scope. Establish a CLA before accepting PRs.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
10

## Slide 11
14-Week Master Roadmap
Parallel execution across all 6 pillars
Chart: 
| Product Depth | Enterprise Readiness | Ecosystem & Integrations | AI Innovation | Brand & GTM | Community & Trust
Start | 0 | 0 | 1 | 0 | 0 | 2
Product Depth | 12 | 0 | 0 | 0 | 0 | 0
Enterprise Readiness | 0 | 10 | 0 | 0 | 0 | 0
Ecosystem & Integrations | 0 | 0 | 13 | 0 | 0 | 0
AI Innovation | 0 | 0 | 0 | 13 | 0 | 0
Brand & GTM | 0 | 0 | 0 | 0 | 14 | 0
Community & Trust | 0 | 0 | 0 | 0 | 0 | 8
Weeks (each unit = 1 week · all pillars execute in parallel)
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
11

## Slide 12
Risk Register
One critical risk per pillar — severity and mitigation
Pillar | Risk | Severity | Probability | Mitigation
Product Depth | Playwright→Gherkin mapping accuracy insufficient for V1 | Critical | High | Start with structured step patterns only. Add NLP resolver in V2. Manual override available.
Enterprise Readiness | SOC 2 observation period delays certification beyond target | Critical | High | Start auditor engagement Week 1. Use automated evidence collection (Vanta/Drata). No delay acceptable.
Ecosystem & Integrations | Atlassian partner review takes longer than 6 weeks | High | Medium | Submit Connect app manifest by Week 7. Engage Atlassian partner team early. Maintain Basic Auth as fallback.
AI Innovation | Fine-tuning quality does not meet QA engineer eval threshold | Critical | Very High | Do not announce model until evaluation passes. Keep GPT-4o as default until TraceLMs-QA model is validated.
Brand & GTM | Stripe subscription event handling errors cause wrong tier billing | High | Low | Idempotent webhook handlers. Store Stripe subscriptionId on Org. Test all subscription lifecycle events in staging.
Community & Trust | Open-source extraction exposes proprietary algorithm or secret | Critical | Low | Full security audit before any code is published. Legal review of CLA. No extraction until audit passes.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
12

## Slide 13
Investment & Resource Requirements
What is needed to execute Phase 6 to Rank-1 standard
Engineering
· 2× Backend Engineers (Node.js/TypeScript) — full-time 14 weeks
· 2× Frontend Engineers (React/TypeScript) — full-time 14 weeks
· 1× DevOps / Infrastructure Engineer — 50% for 14 weeks
· 1× AI/ML Engineer — Weeks 1–12 (fine-tuning pipeline)
Infrastructure
· Supabase Pro plan — pgvector + audit logging + Storage
· GPU compute: Lambda Labs or Modal — fine-tuning runs (Weeks 6–10)
· Together AI or Replicate — model serving after fine-tuning
· Stripe — payment processing (test + live accounts)
· Vanta/Drata — SOC 2 automated evidence collection ($8–15K/yr)
Go-to-Market
· Marketing site development (Next.js/Astro) — Weeks 3–6
· Content programme: 1× technical writer — 2h/week from Week 4
· Atlassian partner registration + review fee
· LLM benchmark infrastructure — compute for 50 req set eval runs
· Legal: CLA review for open-source, GDPR review for EU training data
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
13

## Slide 14
Success Metrics & KPIs
How we measure achievement of Rank-1 status
Pillar | Primary KPI | Target | Measurement Method
Product Depth | Test execution success rate in CI pipeline | ≥ 90% pass rate on Playwright runner | Automated run logs per generation
Enterprise Readiness | SOC 2 Type II certification issued | Certified within 12 months of observation start | Auditor certification letter
Ecosystem & Integrations | Atlassian Marketplace listing live + API adoption | Listed + 50 API integrations in Month 1 | Marketplace install count + API key creation events
AI Innovation | TraceLMs-QA model quality vs GPT-4o-mini | ≥ equivalent quality score at ≤ 1/10th token cost | BLEU + human eval on held-out test set
Brand & GTM | Free-to-paid conversion + organic traffic | ≥ 12% free→paid conversion; 10K monthly visitors | Stripe conversion funnel + Google Analytics
Community & Trust | @tracelms/core GitHub stars + SDK downloads | 500 stars in Month 1; 1,000 npm downloads/week | GitHub Insights + npm download stats
Overall | Product score (Rank-1 benchmark) | 9.6 / 10 | Composite: product depth + trust + ecosystem + market reach
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026
14

## Slide 15
Next Steps & Leadership Decisions
Approvals, budget commitments, and strategic choices needed before Week 1
01
Approve Phase 6 scope and 14-week delivery commitment
Confirm the 44-task scope. Authorize engineering capacity: 4 full-time engineers + 1 AI/ML engineer. Establish weekly delivery reviews.
02
Authorize SOC 2 auditor engagement — start Week 1
Select and contract Vanta, Drata, or Secureframe. SOC 2 Type II observation period begins only when the auditor is engaged. Every week of delay = a week of certification slip.
03
Approve AI model fine-tuning infrastructure spend
GPU compute (Lambda Labs/Modal) for fine-tuning runs in Weeks 6–10. Estimated $2,000–$5,000. Together AI managed serving for post-launch model hosting.
04
Confirm Stripe PRO plan pricing before Weeks 2–3
Freemium enforcement and Stripe integration require the PRO price to be decided before checkout session development begins. Suggested: $X/user/month. Leadership decision required.
05
Approve open-source IP policy and legal review
Open-sourcing @tracelms/core requires legal confirmation of scope (no proprietary algorithms or customer data in extraction). CLA must be in place before any PR is accepted from the community.
TraceLMs Cloud · Phase 6: Rank-1 Strategy · Confidential · June 24, 2026