## Slide 1
TraceLMs Cloud
SaaS Implementation Roadmap
Phases 1 – 6 · 8 Phases · ~39 Weeks · End State: Enterprise-Ready SaaS
June 25, 2026

## Slide 2
The Challenge
Why TraceLMs Cloud requires a structured roadmap
TraceLMs Cloud v0.1.0 — Current State
🔴 No persistence
Generated test cases vanish on every page refresh
🔴 No authentication
Anyone with the URL accesses all API keys and Jira data
🔴 No file security
Uploaded documents pass directly to the LLM — injection risk
🔴 No multi-tenancy
All users share one settings row and one history
🔴 No permissions
A Viewer has identical access to an Owner — no role enforcement
🔴 No prompt control
Improving AI output requires a backend code deployment
The Opportunity
✓ Core AI pipeline is functional and working
✓ Prisma schema already has all required models
✓ SSE streaming delivers real-time generation to browser
✓ Xray push with dedup and retry is production-ready
✓ React frontend architecture is clean and extensible
The foundation is solid.
The gaps are well-defined.
The roadmap is clear.

## Slide 3
TraceLMs Cloud — What It Does
AI-powered test case generation from software requirements → Xray-ready output
Requirements
#TXT · DOCX · PDF · Jira
→
AI Processing
4 LLM Providers
SSE Streaming
→
Test Cases
Gherkin · Steps · Priority
→
Xray Push
Dedup · Retry · Preview
< 5 min
Requirements → test cases
4
LLM providers (OpenAI, Anthropic, Gemini, Groq)
4 formats
.txt · .md · .docx · .pdf
1 click
Xray push with dedup
v0.1.0
Production core pipeline

## Slide 4
The 8-Phase Implementation Strategy
~39 weeks total · Phases 2.5 and 3.5 are bridging phases that close security and access control gaps before the next feature phase ships
Phase 1
Persistence & Reliability
3 wks
Weeks 1–3
Phase 2
Auth & Single-User Security
3 wks
Weeks 3–6
Phase 2.5
Document Security Gateway
1.5 wks
◆ Bridging Phase
Phase 3
Multi-Tenancy & Project Management
5 wks
Weeks 8–13
Phase 3.5
RBAC Foundation
2 wks
◆ Bridging Phase
Phase 4
AI Quality & Prompt Management
4 wks
Weeks 15–19
Phase 5
6 wks
Market Differentiators
"What no other tool can do."
• Bi-directional traceability — test cases linked to requirement clauses
• Regression impact analysis — stale test detection on requirement change
• Stakeholder approval workflow — email review before Xray push
• LLM cost analytics — cost per run, per project, per provider
Weeks 19–25
Phase 6
14 wks
Enterprise Readiness
"Enterprise-grade. SOC 2 ready. Marketplace-listed."
• Full RBAC permission matrix UI (extends Phase 3.5)
• SAML 2.0 / OIDC SSO — Okta, Azure AD, Google Workspace
• SCIM 2.0 user provisioning
• SOC 2 Type II readiness + audit log
• Private file storage + async malware scanning
Weeks 25–39
◆ Bridging phases (2.5 and 3.5) are security gates — not optional scope. They close active vulnerabilities before the next feature phase ships.

## Slide 5
Phase 1 · Persistence & Reliability
Weeks 1–3 · 3 wks
"Work is never lost."
THE PROBLEM
Generated test cases vanish on page refresh. Push history resets on server restart. The tool is unusable beyond a demo.
WHAT WE BUILD
Persist every generation and push record to the database. Load the last generation on page mount. Users gain confidence that TraceLMs Cloud is a reliable working tool, not a scratchpad.
KEY DELIVERABLES
Write completed generations to DB (Generation table)
Load last generation on page load
Persist Xray push history to DB
Remove dead sidebar tabs (Projects, LLM Providers)
BUSINESS VALUE
Retention. Users commit to the tool when their work persists.
ACCEPTANCE KPI
Zero generation loss on refresh · Push history survives restarts

## Slide 6
Phase 2 · Auth & Single-User Security
Weeks 3–6 · 3 wks
"Lock the front door before anyone enters."
THE PROBLEM
Without authentication, anyone with the server URL has full access — all API keys, all Jira connections, all generated test cases. External deployment is impossible.
WHAT WE BUILD
Add email/password login with JWT sessions. Protect every API route. Enforce HTTPS. Add rate limiting. TraceLMs Cloud can now be deployed externally to real teams.
KEY DELIVERABLES
Email/password auth — bcrypt + JWT
Auth middleware on all /api routes
Login page (React)
HTTPS via reverse proxy (Nginx/Caddy)
Rate limiting — per-IP and per-user
Requirement textarea input validation
BUSINESS VALUE
Deployability. The product can leave localhost.
ACCEPTANCE KPI
All /api routes return 401 without JWT · HTTPS enforced · 429 on rate breach

## Slide 7
Phase 2.5 · Document Security Gateway
Weeks 6–8 · 1.5 wks
"Validate the file before the AI ever sees it."
THE PROBLEM
TraceLMs accepts any uploaded file and passes extracted text directly to the LLM — including text like "Ignore previous instructions." This is an active vulnerability in v0.1.0.
WHAT WE BUILD
A typed 7-step DocumentSecurityGateway validates every upload before parsing: extension → size → decode → magic bytes → structure → macro detection → SHA-256 hash. A PromptSanitizer wraps extracted text in data boundaries and flags injection patterns.
KEY DELIVERABLES
DocumentSecurityGateway — 7-step typed validation pipeline
PromptSanitizer — boundary wrap + injection pattern scanner
JSON body limit: 50 MB → 27 MB
Upload rate limit: 10 files / user / min
Unit test coverage for all 7 gateway steps
BUSINESS VALUE
Security posture + SOC 2 CC6.1 evidence. Closes the attack surface before multi-tenancy grows the user base.
ACCEPTANCE KPI
Malformed/macro/oversized files rejected with typed error codes · Injection patterns flagged <2% false positive rate

## Slide 8
Phase 3 · Multi-Tenancy & Project Management
Weeks 8–13 · 5 wks
"One tool, many teams."
THE PROBLEM
TraceLMs Cloud has one shared settings row and one shared history. Multiple users corrupt each other's state. There is no concept of a project, a team, or individual ownership.
WHAT WE BUILD
Activate the existing Prisma schema. Each user gets isolated settings, project history, and a generation log. Teams can collaborate on projects without data collision. The platform becomes billable per user.
KEY DELIVERABLES
User model + foreign keys on Project and Generation
Project CRUD + working Projects tab
Generation history per project
Per-user settings (replaces single shared row)
Stakeholder invite + role label UI
SHA-256 dedup from Phase 2.5 for generation history
BUSINESS VALUE
Team adoption. TraceLMs scales from one person to a department.
ACCEPTANCE KPI
User A cannot access User B's projects · Settings isolation verified · History per project

## Slide 9
Phase 3.5 · RBAC Foundation
Weeks 13–15 · 2 wks
"Role labels become permission boundaries."
THE PROBLEM
Phase 3 introduces role labels but never enforces them. A Viewer has identical server-side capabilities to an Owner. Xray pushes, settings changes, and project deletions are unrestricted.
WHAT WE BUILD
Add OrgRole and ProjectRole enums enforced in Express middleware. Every sensitive route is guarded. UI hides/disables actions the user cannot perform. Phase 6 enterprise RBAC is additive on this foundation.
KEY DELIVERABLES
OrgRole: OWNER / ADMIN / EDITOR / VIEWER — enforced on all routes
ProjectRole: LEAD / EDITOR / REVIEWER / VIEWER
Permission middleware: can() + requireRole()
UI: role badge, disabled destructive actions for Viewer
Owner auto-bootstrap on first registration
User management UI (Owner/Admin only)
BUSINESS VALUE
Data integrity + compliance. Viewer cannot push to Xray. SOC 2 access control evidence.
ACCEPTANCE KPI
Viewer JWT returns 403 on all mutation routes · Role badge visible in sidebar

## Slide 10
Phase 4 · AI Quality & Prompt Management
Weeks 15–19 · 4 wks
"Better output, without a code deploy."
THE PROBLEM
Prompt quality determines test case quality. But all prompts are static files requiring a backend deployment to change. QA teams have no way to tune output for their domain.
WHAT WE BUILD
Store system prompts in the database. Build a prompt management UI. Add per-project prompt overrides. Introduce inline test case editing and a feedback loop that captures thumbs-up/down per test case.
KEY DELIVERABLES
Prompt management UI — edit from browser, stored in DB
Per-project prompt customization
Inline test case editing before Xray push
Generation feedback loop (thumbs per test case)
Model quality scoring per provider
BUSINESS VALUE
Speed-to-quality. Teams produce publication-ready test cases faster with less manual rework.
ACCEPTANCE KPI
Prompt changes live in <2 min with no code release · Feedback loop data persisted per generation

## Slide 11
Phase 5 · Market Differentiators
Weeks 19–25 · 6 wks
"What no other tool can do."
THE PROBLEM
Generic AI test tools generate test cases. TraceLMs Cloud must generate test cases AND maintain their connection to requirements, track cost, and flag requirement quality.
WHAT WE BUILD
Ship five differentiating capabilities: bi-directional traceability, regression impact analysis, stakeholder approval workflow, LLM cost analytics dashboard, and requirement quality scoring.
KEY DELIVERABLES
Bi-directional traceability — test cases linked to requirement clauses
Regression impact analysis — stale test detection on requirement change
Stakeholder approval workflow — email review before Xray push
LLM cost analytics — cost per run, per project, per provider
Requirement quality score — completeness + testability analysis
BUSINESS VALUE
Competitive moat. These capabilities justify a premium price tier and make migration painful.
ACCEPTANCE KPI
Traceability coverage rate tracked · LLM cost per test case displayed · Quality score validated against QA review

## Slide 12
Phase 6 · Enterprise Readiness
Weeks 25–39 · 14 wks
"Enterprise-grade. SOC 2 ready. Marketplace-listed."
THE PROBLEM
Enterprise procurement gates require SSO, SCIM provisioning, SOC 2 Type II, fine-grained access control, and audit logging. Without these, large-organization deals cannot close.
WHAT WE BUILD
Six pillars: Enterprise Security (full RBAC, SAML/OIDC, SCIM), Product Depth, Ecosystem integrations, AI Innovation, Brand & GTM, Community & Trust (SOC 2, public docs).
KEY DELIVERABLES
Full RBAC permission matrix UI (extends Phase 3.5)
SAML 2.0 / OIDC SSO — Okta, Azure AD, Google Workspace
SCIM 2.0 user provisioning
SOC 2 Type II readiness + audit log
Private file storage + async malware scanning
Azure DevOps / GitHub Actions / Zephyr integrations
BUSINESS VALUE
Enterprise revenue. Large-org deals, ISV marketplace listings, compliance certifications.
ACCEPTANCE KPI
SOC 2 Type II report issued · SSO login rate · Enterprise MRR · Marketplace install count

## Slide 13
Implementation Timeline · ~39 Weeks
Bridging phases 2.5 and 3.5 are shown in distinct tones
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
Phase 1
Persistence
W1–W3
Phase 2
Auth & Security
W3–W6
Phase 2.5
Doc Security
W6–W8
Phase 3
Multi-Tenancy
W8–W13
Phase 3.5
RBAC Foundation
W13–W15
Phase 4
AI Quality
W15–W19
Phase 5
Differentiators
W19–W25
Phase 6
Enterprise Readiness
W25–W39
Bridging phases (2.5, 3.5) are critical security gates — they are not optional.

## Slide 14
Investment Summary
Estimated engineering effort across all 8 phases
Phase
Name
Duration
Effort*
Risk
Strategic Gate
Phase 1
Persistence & Reliability
3 weeks
~1 engineer
Low
Must-ship before external access
Phase 2
Auth & Single-User Security
3 weeks
~1–2 engineers
Medium
Must-ship before any external deployment
Phase 2.5
Document Security Gateway
1.5 weeks
~1 engineer
Low-Med
Must-ship before multi-tenancy
Phase 3
Multi-Tenancy & Projects
5 weeks
~2 engineers
Medium
Must-ship for team adoption and billing
Phase 3.5
RBAC Foundation
2 weeks
~1–2 engineers
Med-High
Must-ship before Phase 4 features are gated
Phase 4
AI Quality & Prompt Management
4 weeks
~2 engineers
Medium
Premium tier unlock
Phase 5
Market Differentiators
6 weeks
~2–3 engineers
High
Competitive moat; Phase 6 pull-through
Phase 6
Enterprise Readiness
14 weeks
~3–5 engineers
High
Enterprise sales and marketplace listings
TOTAL
~39 weeks
~14–18 eng-months
End state: Enterprise-ready SaaS
* Effort estimates assume a senior full-stack engineer per unit. Phases can be parallelized with additional engineers.

## Slide 15
Risk Register & Mitigation
Key risks across the 8-phase roadmap
High
Phase 2
Auth middleware regression
→ Full integration test suite covering all /api routes before and after auth middleware is mounted.
High
Phase 3
Settings migration (single row → per-user)
→ Data migration script with rollback. Test against production snapshot in staging before deploy.
High
Phase 3.5
Permission middleware logic error
→ Unit test matrix: every role × every action × expected HTTP status. 100% coverage required.
Medium
Phase 2.5
file-type ESM compatibility with esbuild
→ Use dynamic import() or pin to a CJS-compatible version. Verify bundle output before deploy.
Medium
Phase 4
Prompt DB migration alters default behavior
→ Seed DB with current .txt file content as immutable defaults. User overrides are separate records.
High
Phase 5
Traceability NLP accuracy
→ Validate against 50 real requirement samples before release. Surface confidence score to users.
High
Phase 6
Phase 6 scope (14 weeks) — schedule risk
→ Phase 6 is 6 independently deliverable pillars. Scope by pillar, not as a monolithic release.

## Slide 16
Next Steps
01
Approve roadmap
Confirm phase sequence and resource allocation with engineering leadership
02
Assign Phase 1 engineer(s)
Phase 1 is 3 weeks — can begin immediately on the v0.1.0 codebase
03
Define sprint ceremonies
Each phase maps to 1–2 sprint cycles; establish sprint review gates per phase
04
Establish acceptance criteria sign-off
Phase KPIs (in Summary Excel) become the Definition of Done for each phase
05
Plan Phase 2 security review
Schedule a security review post-Phase 2 before external deployment
06
Scope Phase 6 by pillar
Phase 6 is 14 weeks — assign pillar owners across the team before Phase 5 ends
TraceLMs Cloud · SaaS Roadmap v1.0 · June 25, 2026