## Executive Roadmap Summary
TraceLMs Cloud — Full SaaS Implementation Roadmap ¦ Phases 1 through 6
v0.1.0 base · 8 phases · ~39 weeks total · Generated June 25, 2026 · Audience: Directors, Delivery Head, Product Management, Country Head
Phase | Name | Focus Area | Duration | Timeline | Strategic Intent | Key Deliverables (summary) | Business Value | KPI
Phase 1 | Persistence & Reliability | Foundation | 3 weeks | Weeks 1–3 | Transform TraceLMs Cloud from a demo that loses all work on page refresh into a reliable product where every generation is automatically saved. This is the prerequisite for every other feature — nothing built on top of an ephemeral system has lasting value. | • Write completed generations to the Generation DB table • Load last generation on page load (no lost work on refresh) • Persist push history to DB (replaces in-memory store) • Remove dead Projects/LLM Providers tabs from sidebar | Users trust the tool with real requirements; retention improves | Zero generation loss on page refresh; push history survives restarts
Phase 2 | Authentication & Single-User Security | Security | 3 weeks | Weeks 3–6 | Add the minimum security layer required before TraceLMs Cloud is exposed to any network beyond localhost. Without auth, any person with the URL has full access to all data, all API keys, and all Jira connections. This phase closes that exposure with email/password login, JWT session management, HTTPS enforcement, and general rate limiting. | • Email/password auth — bcrypt hashing + JWT issuance • Auth middleware protecting all /api routes • Login page (React component + route) • HTTPS enforcement via reverse proxy (Nginx or Caddy config) • Rate limiting — per-IP and per-user across all API routes | Product can be deployed externally; API keys and Jira tokens are protected | All /api routes return 401 without valid JWT; HTTPS verified; rate limit returns 429
Phase 2.5 | Document Security Gateway | Security (Upload) | 1.5 weeks | Weeks 6–8 | Close the file upload attack surface before multi-tenancy ships. TraceLMs v0.1.0 passes any uploaded file — regardless of content, type, or embedded instructions — directly to the LLM. This phase adds a typed 7-step validation pipeline (DocumentSecurityGateway), a prompt injection sanitizer (PromptSanitizer), and upload-specific rate limiting. Every future phase inherits these protections at zero additional cost. | • DocumentSecurityGateway.ts — 7-step pipeline: extension → size → decode → magic bytes → structure → macro → SHA-256 • PromptSanitizer.ts — document boundary wrap, injection pattern scanner, flag-and-warn • JSON body limit tightened: 50 MB → 27 MB • Upload rate limit: 10 files / user / minute on /api/parse • Generation rate limit: 5 runs / user / minute on /api/generate | SOC 2 CC6.1/CC7.2 evidence; protects against prompt injection attacks via document upload | Malformed/macro/oversized files return typed error codes; injection patterns flagged with <2% false positives
Phase 3 | Multi-Tenancy & Project Management | Platform | 5 weeks | Weeks 8–13 | Activate the existing Prisma schema — Project, Stakeholder, Generation — for real multi-user team use. TraceLMs Cloud has the data models but no UI or routes to use them. This phase turns the tool from a single-person utility into a team platform: each user has their own settings, each project has its own generation history, and stakeholders can be invited and assigned roles. | • User model with foreign keys on Project and Generation • Project CRUD routes (/api/projects) + working Projects tab UI • Generation history per project (list + detail view) • Settings scoped per user (replaces single shared Settings row) • Stakeholder invite and role label assignment UI | Multiple QA teams can use TraceLMs concurrently without data collision; project-scoped history enables audit | Each user sees only their projects; generation history survives cross-session; invite workflow functional
Phase 3.5 | RBAC Foundation | Security (Access Control) | 2 weeks | Weeks 13–15 | Bridge the gap between Phase 3's stakeholder role labels (stored in DB, displayed in UI, but never enforced) and Phase 6's full enterprise RBAC. Without this phase, a Viewer can push to Xray, change global settings, and delete projects — the same capabilities as an Owner. Phase 3.5 adds OrgRole and ProjectRole enums, enforces them in Express middleware, and reflects them in the UI. | • OrgRole enum: OWNER / ADMIN / EDITOR / VIEWER on User model • ProjectRole enum: LEAD / EDITOR / REVIEWER / VIEWER on ProjectMember • Permission middleware: can() helper + requireRole() + requireProjectRole() • Route guards on all sensitive routes (settings, Xray push, project delete) • AuthContext in React — role available to all components via useAuth() | Data integrity across teams; prevents accidental Xray pushes by observers; SOC 2 access control evidence | Viewer JWT returns 403 on all mutation routes; Owner can manage all users from UI
Phase 4 | AI Quality & Prompt Management | Product Quality | 4 weeks | Weeks 15–19 | Improve generation quality and give teams control over the AI behavior without requiring a code deployment. TraceLMs v0.1.0 uses static prompt files — any change requires a backend deploy. This phase stores prompts in the DB, allows per-project customization, enables inline test case editing before Xray push, and introduces a feedback loop that progressively improves output quality for each team's specific requirements. | • Prompt management UI — view and edit system prompts from the browser • Prompts stored in DB (replaces static .txt files) • Per-project prompt overrides (customize prompts per project without affecting others) • Inline test case editing — edit generated content before Xray push • Generation feedback loop — thumbs up/down per test case | QA teams produce publication-ready test cases without manual rework; prompt tuning reduces iteration cycles | Prompt edits deployable in <2 min with no code release; post-edit Xray push acceptance rate tracked
Phase 5 | Market Differentiators | Competitive Advantage | 6 weeks | Weeks 19–25 | Ship the features that no generic test management tool can replicate — because they require deep AI understanding of the relationship between requirements and tests. These five differentiators position TraceLMs Cloud as the only AI QA platform that closes the full requirements→test→Xray loop with traceability, impact analysis, and cost transparency. | • Bi-directional requirement traceability — link test cases to specific requirement clauses • Regression impact analysis — identify stale tests when requirements change • Stakeholder approval workflow — email notification + review UI before Xray push • LLM cost analytics dashboard — tokens used + estimated cost per run, per project, per provider • Requirement quality score — analyze and score requirements before generation | Traceable test suites; informed LLM cost management; upstream requirement quality gates | Traceability coverage rate; regression suggestions accuracy; LLM cost per test case tracked
Phase 6 | Enterprise Readiness | Enterprise | 14 weeks | Weeks 25–39 | Transform TraceLMs Cloud into an enterprise-grade SaaS platform ready for procurement by large organizations with compliance, SSO, and audit requirements. Six pillars cover enterprise security (SAML/SCIM/full RBAC), product depth (multi-format output, bulk operations), ecosystem integrations (Azure DevOps, GitHub Actions, webhooks), AI innovation (RAG, multi-language, advanced models), brand & GTM (marketplace listings, partner program), and community & trust (SOC 2 Type II, public documentation). | • Full RBAC with fine-grained permission matrix UI (extends Phase 3.5) • SAML 2.0 / OIDC SSO integration (Okta, Azure AD, Google Workspace) • SCIM 2.0 user provisioning • SOC 2 Type II audit readiness (AuditLog model + evidence artifacts) • Private file storage with async malware scanning (Supabase + cloud scanner) | Unlocks enterprise deals; SOC 2 satisfies procurement; SSO removes adoption friction for large orgs | SOC 2 Type II report issued; SSO login rate; enterprise MRR; marketplace install count

## Timeline (Gantt)
TraceLMs Cloud — Implementation Gantt (Weeks 1–39)
Phase | Name | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
Phase 1 | Persistence & Reliability
Phase 2 | Authentication & Single-User Security
Phase 2.5 | Document Security Gateway
Phase 3 | Multi-Tenancy & Project Management
Phase 3.5 | RBAC Foundation
Phase 4 | AI Quality & Prompt Management
Phase 5 | Market Differentiators
Phase 6 | Enterprise Readiness
Phase 2.5 (Doc Security) and Phase 3.5 (RBAC) are bridging phases — they close security gaps that would otherwise exist across multiple feature phases. Total duration ~39 weeks assumes a single cross-functional team of 3–5 engineers.

## Strategic Value
TraceLMs Cloud — Strategic Value per Phase
Phase | Name | Who Benefits | What They Gain | Risk if Skipped | Phase Gate
Phase 1 | Persistence & Reliability | All users | Work is never lost. Generation history survives page refresh and server restart. | No user will rely on a tool that loses their work. Adoption stalls at internal demo stage. | Must complete before Phase 2 — auth requires User-associated persisted data
Phase 2 | Auth & Security | Security, DevOps, Compliance | Protected deployment. Only authenticated users access API keys and Jira connections. | Any public URL exposes all API keys and customer data. Cannot deploy externally. | Must complete before Phase 2.5 — userId needed for upload rate limiting
Phase 2.5 | Document Security Gateway | Security, QA teams, Compliance | Closed upload attack surface. Prompt injection via document upload is blocked. | Authenticated users can inject LLM instructions via uploaded DOCX/PDF. SOC 2 audit fails CC6.1. | Must complete before Phase 3 — multi-tenant upload must be safe before user base grows
Phase 3 | Multi-Tenancy | QA Leads, Product Managers, multiple teams | Team collaboration. Multiple users work in isolated projects without data collision. | Only one team can use TraceLMs at a time. Not scalable. Cannot charge per user. | Must complete before Phase 3.5 — role enforcement requires a User+Project model
Phase 3.5 | RBAC Foundation | QA Leads, Admins, Security | Permission enforcement. Viewers cannot push to Xray or change settings. | A Viewer has identical capabilities to an Owner. SOC 2 access control evidence gaps. | Must complete before Phase 4 — new gated features (prompt editing) need roles to enforce
Phase 4 | AI Quality | QA Engineers, QA Leads | Better test cases, faster. Teams tune prompts without a code deployment. | Output quality is fixed at v0.1.0 level. Prompt improvements require engineering deploys. | Must complete before Phase 5 — differentiators build on editable, high-quality output
Phase 5 | Market Differentiators | Product Managers, QA Leads, Business Analysts | Unique capabilities — traceability, regression analysis, requirement scoring — that no generic tool provides. | TraceLMs competes on price with generic tools instead of on capability. No enterprise pull-through. | Must complete before Phase 6 — enterprise buyers expect these as table-stakes for premium tier
Phase 6 | Enterprise Readiness | Enterprise Buyers, Procurement, CISO | SSO, SCIM, SOC 2, full RBAC, audit log. Enterprise procurement gates satisfied. | Cannot sell to enterprises with security requirements. No marketplace presence. No compliance certifications. | End state — enables enterprise deals, ISV listings, and large-org contracts

## Phase KPIs & Acceptance
TraceLMs Cloud — Phase KPIs & Acceptance Criteria
Phase | Name | Acceptance Criteria / KPI | Risk Level | Status
Phase 1 | Persistence | 1. Generated test cases persist across page refresh. 2. Push history survives server restart. 3. Load last generation on mount in <500ms. 4. No data loss on concurrent writes. | Low | To Do
Phase 2 | Auth & Security | 1. All /api routes return 401 without valid JWT. 2. HTTPS enforced (HTTP redirects to HTTPS). 3. Rate limiter returns 429 after threshold. 4. Bcrypt rounds ≥12. 5. JWT expiry ≤24h. | Medium | To Do
Phase 2.5 | Doc Security | 1. Files with invalid extension return EXT_BLOCKED. 2. Oversized files rejected before Buffer.from(). 3. DOCX with vbaProject.bin returns MACRO_DETECTED. 4. Injection pattern in document returns warning to frontend. 5. False-positive rate on 10 real requirement samples: 0%. | Low-Medium | To Do
Phase 3 | Multi-Tenancy | 1. User A cannot see User B's projects or generations. 2. Settings are scoped per user (changing one does not affect another). 3. Stakeholder invite email delivers within 60s. 4. Generation history list loads in <800ms for 100 records. | Medium | To Do
Phase 3.5 | RBAC | 1. Viewer JWT returns 403 on POST /api/xray/push. 2. Viewer JWT returns 403 on PATCH /api/settings. 3. Owner is auto-assigned to first registered user. 4. Owner cannot demote self if last Owner. 5. Role badge visible in sidebar for all roles. | Medium-High | To Do
Phase 4 | AI Quality | 1. Prompt edits take effect on next generation without code deploy. 2. Per-project prompt override does not affect other projects. 3. Inline test case edits saved before Xray push. 4. Feedback loop: thumbs count stored per test case in DB. | Medium | To Do
Phase 5 | Differentiators | 1. Traceability map links test cases to requirement clauses. 2. Regression analysis identifies stale tests on requirement diff. 3. LLM cost per generation tracked and displayed. 4. Requirement quality score accuracy validated against QA team review. | High | To Do
Phase 6 | Enterprise | 1. SSO login via Okta completes in <3s. 2. SCIM provisioning creates user in <30s. 3. SOC 2 Type II report issued. 4. Audit log captures all mutations with userId + timestamp. 5. Marketplace listing live on at least one ISV platform. | High | To Do